## Nov
HUMAN SETTLEMENTS: DEVELOPMENT & SUPPORT - PROJECT STATUS SUMMARY REPORT - FEBRUARY 2018
GENERAL PROJECT INFO | [10 empty] | TOWNPLANNING |  |  | LAND SURVEYING & PEGGING |  |  | EIA |  | LAND MATTER |  | ENVIRONMENTAL PROCESS |  |  | GENERAL PLAN STATUS |  |  | GEOTECH STATUS |  |  | INFRASTRUCTURE SERVICES |  |  |  | CONSTRUCTION |  |  |  | PROJECT REMARKS
Item |  | Project Manager | Project ID |  | Project Name | GP NUMBER | Funded By: | Ward Number | Project Size (Sites) | Project Type | Date | Consultant | Comments | Date | Consultant | Comments | Date | Consultant | Land Acquisition Status | Land Planning Status | Environmental Impact Assessment | EA Validity | Water Use License (WUL) | GP Approved / not approved | GP Number | Comments | Date | Consultant | Comments | Bulk Infrastructure | Design Consultants | Procurement (Contractor) | Civil Eng. Contractor | Current Project Status | Start Date | End Date | Revised End Date | Comments | Issues | Mitigation Measures | Action By:
1 | COMPLETED PROJECTS | NTOMBI/ ALUNGILE | 20043094 |  | Joe Modise Peace Village Phase 2 | GP 4754/04, 4665/04, 5921/04 | PDOHS | 47 | 429 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 4754/2004, 4665/2004 & 5921/04 |  | Jan 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Kantey & Templer (Pty.) Ltd |  | MMS Developments | Construction of internal services & Top Structures - 100% complete | Aug 2011 | Feb 2013 | April 2013 | Behind Schedule | None | None | None
2 |  |  |  |  | Middle Street Extension |  | USDG | 48 | ±37 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 2260/2002 |  | Sept 2009 | SRK | Available (Ph 1& 2) | Bulks - In place |  |  |  | All internal services (including elec) - complete & site handed over | TBA | TBA | N/A | None | None | None | None
3 |  |  |  |  | Walmer Area O | GP 5290/2008, 2411/2010 | PDOHS | 4 | 437 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 5290/2008, 2411/2010 |  | Aug 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Makhetha Development |  | Simunye Developers | Construction of internal services - in progress (100% complete) | May 2010 | Nov 2010 | June 2013 | Behind Schedule | None | None | None
4 |  |  |  |  | Zosa Street | Draft GP | USDG | 11 | 34 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 208/2013 |  | May 2008 | SRK | Available (Ph 1& 2) | Bulks - In place | SMEC |  |  | Construction of internal services & Top structures - complete | N/A | N/A | N/A | None | None | None | None
5 |  |  | 20110096 | 20110096 | Rosedale Location |  | USDG | [30 empty] | None | None | None | None
6 |  |  |  |  | ● Phase 1 |  |  | 51 | 400 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1296/2012 |  | May 2009 | SRK | Phase 1 & 2 | Bulks - In place | Manong & Associates |  | Izana Cicils | completely serviced | March 2012 | Feb 2013 | May 2014 | Behind Schedule | None | None | None
7 |  |  |  |  | ● Phase 2 |  |  | 51 | 249 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1136/2015 |  | May 2010 | SRK | Phase 1 & 2 | Bulks in place | Manong & Associates |  | TBA | Completely serviced | 2015-02-01 | TBA | N/A |  | People do not want to relocate from serviced area .
8 |  |  | 20130060 |  | Pola Park Extension |  | USDG | 50 | 105 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized | 2017-01-18 | Authorization Pending | No | draft only |  | N/A | N/A | In progress | Bulks - In place | TBA |  | TBA | Completely serviced | TBA | TBA | N/A | None | Testing still needs to be done | None | None
9 |  |  | 20120030 | 20120030 | KwaNobuhle Area 11 |  | USDG | [30 empty] | None | None | None | None
10 |  |  |  |  | ● Phase 1 |  |  | 45 | 350 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | consent issue | May 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Lukhozi Consulting |  | Masakheni | completely serviced | 2013-07-01 | 2015-01-01 | N/A
11 |  |  |  |  | ● Phase 2 |  |  | 45 | 777 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | No | draft only | consent | May 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Lukhozi Consulting |  | Masakheni | Contractor has just commenced with construction of services | 2015-02-01 | TBA
12 |  |  |  |  | Doornhoek |  |  | 48 | 40 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Rapid scan required | Yes | 2381/2001 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | Completely serviced | N/A | N/A | N/A | None | None | None | I&E
13 |  |  |  |  | KwaNobuhle Area 7 Phase 4 |  | USDG | 42 | 244 | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | Yes | Various GP's |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | N/A | N/A | N/A | None | None | None | I&E
14 |  |  |  |  | KwaNobuhle Area 8 Phase 4 |  | USDG | 42 | 266 | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | Yes | Various GP's |  | May 2008 | Bopite | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | N/A | N/A | N/A | None | None | None | I&E
15 |  |  | 20110088 |  | Joe Slovo Uitenhage | Ph1 -GP 865/12 (Ph2 - Draft) | USDG | 48 | 614 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged |  |  | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 865/2012, 1058/2013 |  | Oct 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | BVi Consultants |  | Omega Civils | Completely serviced | May 2012 | April 2013 | 2013-10-01
16 |  |  | 20110094 |  | Mandela & Rolihlahla | Draft GP | USDG | 21 | 218 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 111/2013 & 47/2013 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Worley Parsons |  | Nomaxhosa Construction | Construction of internal services is complete & site handed over | Oct 2011 | Feb 2012 | March 2012 | None | None | None | None
17 |  |  | 20130056 |  | Dikiza Street |  | USDG | 42 | 8 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Rapid scan required | No | draft only | consent issue - with Bhisho (Mr Papu) | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | 2015-07-01 | TBA | N/A | None | None | None | None
18 |  |  |  |  | Ntswahlana Street (Erf. 7916) |  |  | 42 | 10 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 2486/2003 |  | N/A | Bopite | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | 2015-07-01 |  |  |  | None
19 |  |  | 20162364 |  | Kabah Phase 6 (Erf 21647) |  |  | 50 | 54 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Rapid scan required | No | draft only | Council approval for new layout | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | NMBM ( Designed internally) |  | Wavelengths Construction | Project completed , Currently waiting for the liability period to end . | 2015-07-01 | TBA | N/A | None | None | None | None
20 |  |  | 20130038 |  | ERF 8228 KwaNobuhle |  | USDG | 42 | 111 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | No | draft only | few shacks in way-Councillor | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | PDNA |  | TBA | Construction of sevices 100% complete,All the tests passed . | 2015-03-01 | TBA | N/A |  | Termination report still sitting at Legal
49 |  |  | 20162359 |  | Uitenhage (Erf 10015 ,Uitenhage) |  |  | 49 | 12 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | TBA | Construction of internal services is complete |  |  |  |  | None
50 |  |  | 20162363 |  | Rosedale (Erf 12872 , Uitenhage) |  |  | 49 | 30 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | Masiphumelele Trading | Construction of internal services is complete |  |  |  |  | New development. No community issues yet.
21 |  |  | 20130060 |  | Polla Park (Erf 28487, Uitenhage) |  | USDG | 51 | 117 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Bush Clearing - Underway | N/A | N/A | Municipal Owned | Approved | Authorized |  | N/A | No | draft only | ready to lodge GP | N/A | N/A | Not Available | Bulks - In place | ILISO |  | TBA | 80% complete , Constructuction will be complete by the 22nd of August. | 2015-02-01 | TBA | N/A |  | EME's have not been paid
5 |  | RAYNO |  |  |  |  | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | Busy amend layout/GP to avoid construction delay | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services is complete & site handed over | Nov 2012 | April 2013 | May 2013 | None | None | None | None
22 |  |  |  |  | KwaNontshinga |  | USDG | 20 | 105 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1422/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Arcus Gibb Consulting |  | Ascon Trading | Construction of internal services is complete & site handed over |  | Sept 2013 | March 2013 | Behind Schedule | None | Arcuss give to provide the certificates | Consultant (Arcus Gibb)
3 | [5 empty] | Draft GP | USDG | [11 empty] | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 111/2013 & 47/2013 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Worley Parsons |  | Nomaxhosa Construction | Construction of internal services is complete & site handed over | Oct 2011 | Feb 2012 | March 2012 | None | None | None | None
4 | [6 empty] | USDG | [11 empty] | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 2260/2002 |  | Sept 2009 | SRK | Available (Ph 1& 2) | Bulks - In place |  |  |  | All internal services (including elec) - complete & site handed over | TBA | TBA | N/A | None | None | None | None
23 |  |  | 20120042 |  | Sisulu Village Phase 2 (Hlalani Qeqe) |  | USDG | 26 | 18 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 15/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services - 100% complete,ready for top structures | Nov 2012 | April 2013 | May 2013 |  | None | None | None
24 |  |  | 20110090 |  | Roos Street | GP 4271/09 | USDG | 10 | 28 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 4271/2009 |  | May 2008 | SRK | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services is complete & site handed over | Nov 2012 | March 2013 | July 2013 | Behind Schedule | None | None | None
25 |  |  | 20110097 |  | Motherwell High Density |  | USDG | 58 | 109 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | Busy amend layout/GP to avoid construction delay | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services is complete & site handed over | Nov 2012 | April 2013 | May 2013 | None | None | None | None
26 |  |  | 20110092 |  | Missionvale Garden Lots (Phase 1 & 2) |  |  | 32 | 929 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 218/2009, 3478/2011 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Sigodi Marah Martin |  |  | Construction of internal services- 100% complete ¦ Top Structures 100% complete | Aug 2012 | May 2013 | May 2016 | May 2015 | None | May 2017 | May 2018
27 |  |  | 20110092 |  | Missionvale Garden Lots |  | USDG |  |  | Human Settlements Project (Greenfields)
28 |  |  |  |  | ● Phase 3,4 & 5 |  |  | 31 | 1483 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 4459/2009, 5259/09 & 6017/09 |  | N/A | N/A | Available (Ph 1, 2, 3 & 5) |  | EAS |  |  | Construction of internal services- 100% complete ¦ Top Structures 90% complete | Jan 2014 | Jun 2014 | Jun 2016 | None | unblocking of sewer, checking watermeters and internal plumbing of houses. | None | None
29 |  |  | 20120052 |  | Walmer Q Phase 3 |  | USDG | 4 | 188 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | part of G West | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Makhetha Development |  | Power Construction | Construction of internal services - in progress (100% complete) | Oct 2012 | Aprli 2013 |  | On Schedule | None | None | None
56 |  |  | 20120054 |  | Walmer Airport Valley - Section A |  | USDG | 4 | 317 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | relocation | N/A | N/A | Available (Ph 1 & 2) | Bulks - In place | Makhetha Development Consultants | Section A - Complete | Omega Civils | Construction of internal services- 100% complete | 2015-11-01 | 2016-09-01 | 2017-09-01 | None | None
30 |  |  | 20110095 |  | Red Location |  | USDG | 15 | 172 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 901/2012 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Goba Consulting Eng. |  | SJW | Construction of internal services- 100% complete | May 2013 | Oct 2013 | Jun 2014 |  | None
31 |  | NWABISA | 20110091 |  | Khayamnandi Extension |  | USDG
32 |  |  |  |  | ● Phase 1a & 1b |  | USDG | 41 | 471 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 98/2013, 883/2013 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Masakeni Construction | Construction of internal services - 100% complete | Aug 2012 | Sept 2013 | May 2014 | On Schedule | Awaiting WUL | None | Uhambiso
33 |  |  |  |  | ● Phase 2 |  | USDG | 41 | 1013 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 876/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Civils 2000 | Construction of internal services - 100% complete | Aug 2012 | Sept 2013 | May 2014 | None | None | None | None
34 |  |  |  |  | ● Phase 3 |  |  | 52 | 206 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 16/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place |  |  |  | Construction of internal services - 100% complete | June 2013 | May 2014 | Dec 2014 | None | None | None | None
35 |  |  |  |  | ● Phase 4a |  | USDG | 41 | 358 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1268/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Civils 2000 | Construction of internal services - 100% complete | April 2013 | June 2014 | Dec 2014 | None | None | None | None
36 |  |  |  |  | ● Phase 4b |  |  | 41 | 372 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1268/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Masakeni Construction | Construction of internal services - 100% complete | April 2013 | June 2014 | Dec 2014 | None | None | None | None
37 |  |  | 20130019 |  | Motherwell NU12 |  | USDG | 54 | 350 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Pre - ECA | No | Draft only | With SG | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Hemsley & Mydral |  | Masakeni Construction | Construction of internal services- (100% complete) | March 2013 | July 2013 | July 2014 | None | None | None | None
38 |  |  |  |  | Phase 2 (Qaqawuli) |  |  |  | 491 | Disadvantaged Project Area (In-situ) | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | Municipal Owned | Approved | Authorized - NO EA Required |  |  | No | draft only | relocation | Sep 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | KCS Consultants |  | TBA | Phase 2 - at practical completion stage , left with snags | TBA | TBA | N/A |  | None
39 |  |  | 20110093 |  | Motherwell NU29 |  | USDG | 54 | 3478
40 |  |  |  |  | ● Phase 1 |  |  | 54 | 1335 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 5412/02 & 2404/2002 |  | Feb 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services & Top Structures- 100% complete | Jul 2012 | March 2013 | End March 2013 |  | None | None | None
41 |  |  |  |  | ● Phase 2 Stage 1 |  |  | 54 | 1253 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1097/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services is complete & site handed over
42 |  |  |  |  | ● Phase 2 Stage 2 |  |  | 54 | 890 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 586/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services is complete & site handed over |  | March 2013 | May 2013 | Behind Schedule | None | None | None
43 |  |  |  |  | Motherwell NU30 | Draft GP | USDG | 54 | 2067 |  | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | TBA | [8 empty] | Oct 2009 | SRK |  |  | Goba ¦ Izizwe Consultants |  | Masakheni |  | Mar 2014 | Mar 2015 | N/A | None | Farmer's issues | Department of Agriculture to intervene | None
44 |  |  |  |  | ● Phase 1 |  |  | 54 | 605 | Human Settlements Project (Greenfields) | [8 empty] | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1014/2014 |  | Oct 2010 | SRK | Available (Ph 1& 2) | Bulks - Under Planning |  |  |  | Phase 1 - Construction underway 100% complete |  |  | Nov 2015
45 |  |  |  |  | ● Phase 2 |  |  | 54 | 800 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1181/2013 |  | Oct 2010 | SRK | Available (Ph 1& 2) | Bulks - Under Planning |  |  |  | Phase 2 - Construction underway 100% complete | Jan 2015 | Jan 2017 | N/A |  | None
46 |  |  | 20120060 |  | Masakhane Village |  | USDG | 24 | 125 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Authorized - No WUL required | No | draft only | Consent outstanding (PK) | Sep 2010 | SRK | Available (Ph 1& 2) | Bulks - In place | Eyethu Consultants |  | TBA | RoD and WULA are in place. Construction underway | TBA | TBA | N/A | None | No social issues at this stage | None | None
47 | [6 empty] | USDG
7 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 5412/02 & 2404/2002 |  | Feb 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services & Top Structures- 100% complete | Jul 2012 | March 2013 | End March 2013 |  | None | None | None
8 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 1097/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services is complete & site handed over
9 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 586/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services is complete & site handed over |  | March 2013 | May 2013 | Behind Schedule | None | None | None
10 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 15/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services - 100% complete,ready for top structures | Nov 2012 | April 2013 | May 2013 |  | None | None | None
11 | [5 empty] | GP 4271/09 | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 4271/2009 |  | May 2008 | SRK | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services is complete & site handed over | Nov 2012 | March 2013 | July 2013 | Behind Schedule | None | None | None
12 | [5 empty] | GP 5290/2008, 2411/2010 | PDOHS |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 5290/2008, 2411/2010 |  | Aug 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Makhetha Development |  | Simunye Developers | Construction of internal services - in progress (100% complete) | May 2010 | Nov 2010 | June 2013 | Behind Schedule | None | None | None
13 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | No | Draft only | part of G West | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Makhetha Development |  | Power Construction | Construction of internal services - in progress (100% complete) | Oct 2012 | Aprli 2013 |  | On Schedule | None | None | None
14 | [5 empty] | Draft GP | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 208/2013 |  | May 2008 | SRK | Available (Ph 1& 2) | Bulks - In place | SMEC |  |  | Construction of internal services & Top structures - complete | N/A | N/A | N/A | None | None | None | None
15 | [5 empty] | Ph1 -GP 865/12 (Ph2 - Draft) | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | [6 empty] | RoD available | Yes | 865/2012, 1058/2013 |  | Oct 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | BVi Consultants |  | Omega Civils | Construction of internal services - in progress (100% complete) | May 2012 | April 2013 | 2013-10-01
16 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 218/2009, 3478/2011 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Sigodi Marah Martin |  |  | Construction of internal services- 100% complete ¦ Top Structures 100% complete | Aug 2012 | May 2013 | May 2016 | May 2015 | None | May 2017 | May 2018
17 | [6 empty] | USDG
18 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 4459/2009, 5259/09 & 6017/09 |  | N/A | N/A | Available (Ph 1, 2, 3 & 5) |  | EAS |  |  | Construction of internal services- 100% complete ¦ Top Structures 90% complete | Jan 2014 | Jun 2014 | Jun 2016 | None | unblocking of sewer, checking watermeters and internal plumbing of houses. | None | None
19 | [6 empty] | USDG
20 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 98/2013, 883/2013 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Masakeni Construction | Construction of internal services - 100% complete | Aug 2012 | Sept 2013 | May 2014 | On Schedule | Awaiting WUL | None | Uhambiso
21 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 876/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Civils 2000 | Construction of internal services - 100% complete | Aug 2012 | Sept 2013 | May 2014 | None | None | None | None
22 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A |  |  |  |  | RoD available | Yes | 16/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place |  |  |  | Construction of internal services - 100% complete | June 2013 | May 2014 | Dec 2014 | None | None | None | None
23 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A |  |  |  |  | RoD available | Yes | 1268/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Civils 2000 | Construction of internal services - 100% complete | April 2013 | June 2014 | Dec 2014 | None | None | None | None
24 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A |  |  |  |  | RoD available | Yes | 1268/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Masakeni Construction | Construction of internal services - 100% complete | April 2013 | June 2014 | Dec 2014 | None | None | None | None
25 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | Pre - ECA | No | Draft only | With SG | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Hemsley & Mydral |  | Masakeni Construction | Construction of internal services- (100% complete) | March 2013 | July 2013 | July 2014 | None | None | None | None
26 | [5 empty] | Draft GP | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 905/2012, 919/12, 921/12 & 183/12 |  | Oct 2009 | SRK | Phase 1 & 2 | Bulks - In place | Bosch Stemele Consulting |  | Masakeni Construction | Construction of internal services - (100% complete) | May 2012 | May 2013 | July 2014 | Behind Schedule | None | None | None
27 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  | Environmental Exemption |  | RoD available | Yes | 901/2012 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Goba Consulting Eng. |  | SJW | Construction of internal services- 100% complete | May 2013 | Oct 2013 | Jun 2014 |  | None
28 | [6 empty] | USDG | [30 empty] | None | None | None | None
29 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 1296/2012 |  | May 2009 | SRK | Phase 1 & 2 | Bulks - In place | Manong & Associates |  | Izana Cicils | completely serviced | March 2012 | Feb 2013 | May 2014 | Behind Schedule | None | None | None
30 | [6 empty] | USDG | [30 empty] | None | None | None | None
31 | [10 empty] | N/A | N/A | Underway | N/A | N/A | Not Pegged | TBA | TBA |  |  |  |  | RoD available | No | Draft only | consent issue | May 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Lukhozi Consulting |  | Masakheni | completely serviced | 2013-07-01 | 2015-01-01 | N/A
32 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA |  |  |  |  | Rapid scan required | Yes | 2381/2001 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | Completely serviced | N/A | N/A | N/A | None | None | None | I&E
33 | [6 empty] | USDG |  |  |  | N/A | N/A | Not Available | N/A | N/A | Pegged | TBA | TBA |  |  |  |  | RoD available | Yes | Various GP's |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | N/A | N/A | N/A | None | None | None | I&E
34 | [6 empty] | USDG |  |  |  | N/A | N/A | Not Available | N/A | N/A | Pegged | TBA | TBA |  |  |  |  | RoD available | Yes | Various GP's |  | May 2008 | Bopite | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | N/A | N/A | N/A | None | None | None | I&E
48 | PROJECTS UNDER IMPLEMENTATION | NTOMBI/ ALUNGILE | 20120059 |  | Chatty Jachtvlakte |  | USDG | 41 | ±12000 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Partially Pegged | N/A | N/A | Municipal Owned | Approval Pending | Authorized | 2017-09-22 |  | No | nil |  | N/A | N/A | Underway | Bulks - Under Planning | Aurecon |  | Tecni Civils | The contractor has since started with site establishment for HS 5b ,on Wednesday the 2nd of August 2017. | TBA | TBA | N/A | None | HS 5b is under implementation , Budget provision has been made for HS 5b to be implemented by next financial year | None | None
51 |  |  | 20162365 |  | Uitenhage (Erf 12931) |  |  | 49 | 35 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | TBA | Sewer and water is 100% complete , I&E to appoint contractor for road construction |  |  |  |  | Might go above the budget , because the earthworks were nor included and the are is steepy nedds to be evened out
52 |  |  | 20162361 |  | McCarthy Land (Erf 6480 , Afghanistan) |  |  | 48 | 43 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A |  | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | TBA | On the way to I&E |  |  |  |  | Land invasion isuues and eviction orders issued.
53 |  |  | 20162360 |  | Uitenhage (Erf 3179) |  |  | 48 | 42 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A |  | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | Masiphumelele Trading | Sewer and water is 100% complete , The contractor is busy roads . |  |  |  |  | New development. No community issues yet.
54 |  |  | 20120030 |  | KwaNobuhle Area 11 |  | USDG | [30 empty] | None | None | None | None
55 |  |  | 20120030 |  | ● Phase 3a and 3b |  | USDG | 45 | 319 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Not Pegged |  |  | Municipal Owned | Council Approved - COGTA Confirmation Pending | Authorized |  | Authorized | No | nil |  |  |  | Available (Ph1 &2) | Bulks in progress | Lukhozi Consulting |  | TBA | Phase 3a is 66% complete ,Phase 3b also under construction | TBA | TBA | N/A |  | No social issues at this stage
57 |  |  | 20120059 |  | Malabar Ext. 6 Phase 2 |  | USDG | 12 | 671 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Land Surveyor appointed. Phase 1 pegged. Relocation complete for Phase 2. | N/A | N/A | Municipal Owned | Approved | Authorized | 2018-10-02 | Approved | No | nil | Land surveyor busy with draft gp. | N/A | N/A | Available (Ph 1) | Bulks - In place, but upgrading of portions required. | IX Engineers | Phase 1 and Phase 2 complete. | Phase 1 - Raubex Strata | Phase 1 - is currently under construction ,currently at 70 % completion. Phase 2 is due for Spec, appointment expected in June 2019. | TBA | 2018-05-01 | N/A | None | Phase 1 progress well with anticipated completion by April 2108. | None | None
58 |  | NWABISA | 20110091 |  | Khayamnandi Extension |  | USDG
59 |  |  |  |  | ● Phase 6 North |  |  | 41 | 402 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | 90% Complete | TBA | TBA | N/A | None | None | None
60 |  |  | 20120053 |  | MK Silvertown 2 Qaqawuli |  | USDG | 16 | [29 empty] | None |  | None | Properties
61 |  |  |  |  | ● Phase 1 (MK Silvertown) |  |  |  | 275 | Disadvantaged Project Area (In-situ) | N/A | N/A | Draft Available | N/A | N/A | Pegged | TBA | TBA |  |  |  |  | RoD available | No | draft only | relocation | Sep 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | KCS Consultants |  | TBA | 90% Complete | TBA | TBA | N/A
61 |  |  |  |  | ● Phase 2 (Qaqawuli) |  |  |  | 491 | Disadvantaged Project Area (In-situ) | N/A | N/A | Draft Available | N/A | N/A | Pegged | TBA | TBA |  |  |  |  | RoD available | No | draft only | relocation | Sep 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | KCS Consultants |  | TBA | 90% Complete | TBA | TBA | N/A
62 | PROJECTS UNDER PLANNING | NTOMBI/ ALUNGILE | 20120059 |  | Chatty Jachtvlakte |  | USDG | 41,29 | ±12000 | Human Settlements Project (Greenfields) | N/A | N/A | complete | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approval Pending | Authorized | 2017-09-22 |  | No | nil |  | N/A | N/A | Underway | Bulks - Under Planning | Aurecon |  | Tecni Civils | The contractor has commenced with work on site and the project is under construction. | TBA | TBA | N/A | None | No social issues at this stage | None | None
[5 empty] | ● HS 5B |  | USDG | 41,29 | 687 | Human Settlements Project (Greenfields) | N/A | N/A | complete | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approval Pending | Authorized | 2017-09-23 |  | No | nil |  | N/A | N/A | Underway | Bulks - Under Planning | Aurecon |  |  | 90% Complete | TBA | TBA | N/A | None | No social issues at this stage
[5 empty] | ● HS 5A |  | USDG | 41,29 | 562 | Human Settlements Project (Greenfields) | N/A | N/A | complete | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approval Pending | Authorized | 2017-09-24 |  | No | nil |  | N/A | N/A | Underway | Bulks - Under Planning | Aurecon |  |  | Been to BAC | 2019-03-19 |  |  |  | No social issues at this stage
[5 empty] | ● HS 5C |  | USDG | 41,29 | 714 | Human Settlements Project (Greenfields) | N/A | N/A | complete | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approval Pending | Authorized | 2017-09-25 |  | No | nil |  | N/A | N/A | Underway | Bulks - Under Planning | Aurecon |  |  | Due for Spec Comm before end of fin year 2018/19 |  |  |  |  | No social issues at this stage
[5 empty] | ● HS 8 |  | USDG | 41,29 | 502 | Human Settlements Project (Greenfields) | N/A | N/A | complete | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approval Pending | Authorized | 2017-09-26 |  | No | nil |  | N/A | N/A | Underway | Bulks - Under Planning | Aurecon |  |  | Due for Spec Comm before end of fin year 2018/20 |  |  |  |  | No social issues at this stage
63 |  |  | 20120030 |  | KwaNobuhle Area 11 |  | USDG | [30 empty] | None | None | None | None
64 |  |  | 20120030 |  | ● Phase 4 |  | USDG | 45 | 508 | Human Settlements Project (Greenfields) | N/A | N/A | complete | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Council Approved - COGTA Confirmation Pending | Authorized |  | Authorized | No | nil |  |  |  | Available (Ph1 &2) | Bulks in progress | Lukhozi Consulting |  | TBA | Phase 4 is under construction 30% complete | TBA | TBA | N/A |  | None
[5 empty] | ● Phase 5 |  | USDG | 45 | 247 | Human Settlements Project (Greenfields) | N/A | N/A | complete | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Council Approved - COGTA Confirmation Pending | Authorized |  | Authorized | No |  |  |  |  | Available (Ph1 &2) | Bulks in progress | Lukhozi Consulting |  |  | Phase 5 is at Evaluation stage, currently looking at possibility of implementing this financial year 2018/19
[5 empty] | ● Phase 6 |  | USDG | 45 | 537 | Human Settlements Project (Greenfields) | N/A | N/A | complete | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Council Approved - COGTA Confirmation Pending | Authorized |  | Authorized | No |  |  |  |  | Available (Ph1 &2) | Bulks in progress | Lukhozi Consulting
65 |  |  | 20162370 |  | Uitenhage (Erf 818-863) |  | USDG | 51 | 131 | Disadvantaged Project Area (In-situ) | N/A |  | complete | N/A | N/A | Pegged | TBA | TBA | [5 empty] | No | nil | [5 empty] | NMBM ( Designed internally) |  | TBA | At Construction Stage |  |  |  |  | New development. No community issues yet.
66 |  |  |  |  | Witteklip |  | USDG | 40 | 256 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned - Land Ownership Challenged | Approved | Residential Component Authorized; Bulk Component challenged | Residential OK |  | No | nil |  | N/A | N/A | Not Available | Bulks - Under Planning | TBA |  | TBA | Awaiting technical report from Waste Water & Conveyance wrt the type of sanitation to be used. | TBA | TBA | N/A | None | None | None | None
59 |  |  |  |  | Uitenhage (Erf 29669) |  |  | 50 | 19 | Disadvantaged Project Area (In-situ) |  | 29669 | V14B-X-9 | [5 empty] | Municipal Owned | Approved |  |  |  | No | Draft GP | [8 empty] | At preliminary designstage |  |  |  |  | New development. No community issues yet.
67 |  |  |  |  | Uitenhage (Erff 7927) |  |  | 49 | 13 | Disadvantaged Project Area (In-situ) | [8 empty] | Municipal Owned | [14 empty] | At preliminary designstage |  |  |  |  | New development. No community issues yet.
68 |  | RAYNO | 20110094 |  | Mandela Village | Draft GP | USDG | 18 | 71 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned |  |  |  | RoD available | No | draft only | relocation process | Sept 2008 | SRK | Phase 1 & 2 | Bulks - In place | Worley Parsons |  | Masakeni Construction | Construction of internal services (50% complete) - put on hold (awaiting relocations) | TBA | TBA | N/A | None | Resistance to relocation. Anticipated project completion was in 2010. | None | Social Development
69 |  |  | 20130054 |  | Bethelsdorp (Extension 32, 34 & 36) |  | USDG | 37 | TBA | Human Settlements Project (Greenfields) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned |  | Awaiting feedback from DEDEAT on process to be followed. |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place | Gilgal Development Consultants and Project Managers |  | TBA | Consultants submited Prelim Design Report , Awaiting feedback from DEDEAT to identify which EIA process to be followed. | TBA | TBA | N/A | None | Awaiting feedback from Environmental Management wrt EIA process to be followed. | None | None
70 |  |  | 20120031 |  | Ekuphumleni |  | USDG | 19 | 191 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Portions Pegged. Pegging to be completed. | N/A | N/A | Municipal Owned | Approved | Authorized - NO EA Required | Not applicable | N/A | No | draft only | relocations were done and repositioning took place. | N/A | N/A | Available (Ph 1) | Bulks - In place | Arcuss Gibb |  | TBA | Relocation are done, currently filling of sites in progress. The project has been through the Bid Spec committee already and other following processes are underway. | TBA | TBA | N/A | None | Relocation kick-started. To start new procurement process for construction to commence in 2018/19. | De-densify existing shacks | Social Development
71 |  |  | 20120048 |  | N2 North [Grogro] |  |  | 39 | ±2000 | Human Settlements Project (Greenfields) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | In Progress | DEDEAT Refusal |  | Awaiting approval | No | nil |  | N/A | N/A | Phase 1 Available | Bulks - Under Planning | UWP/Iliso |  | TBA | DEDEAT refusal of project. Currently busy with appeal process. | TBA | TBA | N/A | None | Project processes stagnant until appeal process concluded | None | None
72 |  |  |  |  | Kalipa |  | USDG | 19 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Approved | Authorized - NO EA Required |  |  | No | nil |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA |  | TBA | TBA | N/A | None | No social issues at this stage | None | None
73 |  |  | 20120062 |  | Kuyga Phase 3 |  | USDG | 40 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Land issue¦ Provincial Land | Planning pending appointment of lead consultant | EIA dependent on land acquisitioning |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place |  |  | TBA | Initial project planning stages - Awaiting completion of Bulk Sewer Rising Main.¦ Letter to be submitted to Province for availability of land. | TBA | TBA | N/A | None | Availability of land. | None | None
75 |  |  |  |  | Singaphi |  | USDG | 15 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | To be approved | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized - NO EA Required |  |  | No | nil |  | N/A | N/A | Not Required | Bulks - In place | TBA |  | TBA | To formalize the Town Planning layout | TBA | TBA | N/A | None | None | None | Land Planning
76 |  |  | 20120054 |  | Walmer Gqeberha Developments |  |  | 4 | 3500 | Greenfields and In-situ Developments |  |  | approved | n/a | [19 empty] | LOA issued to the contractor. EME meeting not fruitful. Engagements with EMEs were done to resolve work packages. Progress is expected to run smoothly |  |  |  | None |  | None | None
[5 empty] | ● Walmer Airport Valley Roads |  | USDG | 4 | TBA | Foramilazation of informal roads | N/A | N/A | approved | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  |  | draft | nil |  | N/A | N/A | Not Available | Bulks - In place | Makhetha Development Consultants | complete | Khayelihle | Site establishment underway | 2019-03-25 | TBA | N/A |  | Late start due to EME issues
77 |  |  | 20120054 |  | ● Walmer Airport Valley Section B |  | USDG | 4 | TBA | Human Settlements Project (Greenfields) | N/A | Metroplan | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place | Makhetha Development Consultants | delayed due to 1948 slow progress | n/a | awaiting completion of erf 1948 to allow for relocations | TBA | TBA | N/A |  | Slow Suplly Chain processes.
[5 empty] | ● Walmer Airport Valley Section C |  | USDG | 4 | TBA | Human Settlements Project (Greenfields) | N/A | Metroplan | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place | Makhetha Development Consultants | delayed due to 1948 slow progress | n/a | awaiting completion of erf 1948 to allow for relocations | TBA | TBA | N/A |  | Slow Suplly Chain processes.
78 |  |  | 20120054 |  | ● Walmer Erf 11305 |  | USDG | 4 | TBA | Human Settlements Project (Greenfields) | N/A | Metroplan | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | FEIR Pending Authorization |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place | Makhetha Development Consultants | N/A | n/a | Awaiting EIA authorization | TBA | TBA | N/A |  | None
79 |  |  | 20120054 |  | ● Walmer Erf 1948 TRA |  | USDG | 4 | TBA | Temporary Relocation Area | N/A | Metroplan | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  |  | No | nil |  |  |  | Not Available | To be identified during design phase | Makhetha Development Consultants | delayed due to objection by the tenderers. Process is now being finalized. | n/a | Awaiting formal legal confirmation that the project can commence based on the current EIA approval. | TBA | TBA | N/A |  | N/A
80 |  |  |  |  | Seaview / Clarendon Marine |  |  | 40 | TBA | Human Settlements Project (Greenfields) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal and PDHOS: Viability of land development challenged by environmental considerations | Approved | Municipal land rejected - Private land received authorization |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - Under Planning | Gilgal Development Consultants and Project Managers |  |  | Awaiting Land Acquisition process to be concluded for private land | TBA | TBA | N/A |  | Land Acquisition to be concluded.
81 |  | NWABISA |  |  | Khayamnandi Extension |  |  | 205 | 4586 | Human Settlements Project (Greenfields) | [8 empty] | Municipal Owned | Approved | Authorized |  | Authorized
82 |  |  |  |  | Phase 5 |  |  | 41 | 939 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | Procurement process of a contractor is underway | TBA | TBA | N/A | None | None | None
83 |  |  |  |  | Phase 7 |  |  | 41 | 1079 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | Designs under the approval process by I&E | TBA | TBA | N/A | None | None | None
84 |  |  |  |  | Phase 8 |  |  | 41 | 1009 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | No designs as yet | TBA | TBA | N/A | None | None | None
85 |  |  |  |  | Phase 9 |  |  | 41 | 1017 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | No designs as yet | TBA | TBA | N/A
86 |  |  |  |  | Phase 10 |  |  | 41 | 542 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | No designs as yet | TBA | TBA | N/A
88 |  |  | 20120061 |  | Motherwell NU31 |  | USDG | 54 | TBA | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | Bulk Infrastructure challenges | TBA |  | TBA | Bulk services to be sorted out | TBA | TBA | N/A | None | Farmer's issues | Department of Agriculture to intervene | HS: Development & Support
89 |  |  |  |  | Ramaphosa West |  | USDG | 56 | TBA | Human Settlements Project (Greenfields) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Pending Planning | Rapid scan required |  |  | No | nil |  | May 2008 | Bopite | Available (Ph 1& 2) | Bulks Challenged | TBA |  | TBA | Undergoing SALT process | TBA | TBA | N/A | None | Social instability | None | None
90 |  |  | 20130057 |  | Kleinskool Kliprand |  | USDG | 34 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned and portions private land | Pending Planning | EIA Required |  |  | No | nil |  | N/A | N/A | Not Available | To be finalized during planning process | Gibb |  | TBA | Land acquisition is underway. LOA issued to Consultant to commence with planning process. | TBA | TBA | N/A | None | Portion of community residing on privately-owned land. | None | None
91 |  |  | 20120051 |  | Nkatha Seyisi |  | USDG | 19 | 72 | Disadvantaged Project Area (In-situ) | N/A | N/A | To be approved | N/A | N/A | Not Pegged | TBA | Aurecon | Municipal Owned | Pending Planning | To appoint EAP |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place | Gibb |  | TBA | LOA issued to Consultant to start with planning processes.¦ Tender document to be signed | TBA | TBA | N/A | N/A | Awaiting feedback for HIA ¦ Preliminary reports submitted for review ¦ Topographical Survey and Geotechnical Investigation under-way. | None | None
92 |  |  |  |  | Raymond Mhlaba (Buyambo) |  | USDG | 21 | 50 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | Aurecon | Municipal Owned | To be confirmed | Authorized | 2014-09-22 |  | No | draft only | Consent required (PK) | N/A | N/A | Not Available | Bulks - In place | AHS |  | TBA | Construction is almost complete, anticipated to finish end of September 2017. | TBA | TBA | N/A | None | No social issues at this stage | None | None
93 |  |  |  |  | Tyinira Endlovini |  | USDG | 57 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Planning pending appointment of lead consultant | Rapid scan required |  |  | No | nil |  | N/A | N/A | Not Available | Bulks Challenged | TBA |  | TBA | Initial project planning stages | TBA | TBA | N/A | None | Social instability | None | None
95 | FUTURE PROJECTS |  |  |  | Allanridge West (Uitenhage) |  |  | 49 | 201 |  |  |  | B-LD 209 | [20 empty] | On the way to I&E |  |  |  |  | Land invasion isuues and eviction orders issued.
96 |  |  |  |  | McCarthy Land (Erf 17585 , Rosedale) |  |  | 49 | 101 |  |  | 17585 | B-LD 209 | [20 empty] | On the way to I&E |  |  |  |  | Land invasion isuues and eviction orders issued.
97 |  |  |  |  | Uitenhage (Erf 26022) | [28 empty] | On the way to I&E |  |  |  |  | New development. No community issues yet.
98 |  |  |  |  | Wintehoek Park | [28 empty] | EIA Issue |  |  |  |  | New development. No community issues yet.
99 |  |  |  |  | Uitenhage (Erf 7939) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
100 |  |  |  |  | Uitenhage (Erf 8061) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
101 |  |  |  |  | Uitenhage (Erf 9498) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
102 |  |  |  |  | Uitenhage (Erf 12591) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
103 |  |  |  |  | Uitenhage (Erf 12592) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
104 |  |  |  |  | Uitenhage (Erf 15154) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
105 |  |  |  |  | Uitenhage (Erf 15831) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
106 |  |  |  |  | Uitenhage (Erf 16015) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
107 |  |  |  |  | Uitenhage (Erf 17547) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
108 |  |  |  |  | Uitenhage (Erf 17639) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
109 |  |  |  |  | Uitenhage (Erf 23247) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
110 |  |  |  |  | Uitenhage (Erf 24078) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
111 |  |  |  |  | Uitenhage (Erf 26020) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
112 |  |  |  |  | Uitenhage (Erf 26022) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
113 |  |  |  |  | Uitenhage (Erf 8043) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
114 |  |  |  |  | Uitenhage (Erf 16040) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
115 |  |  |  |  | Uitenhage (Erf 26848) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
116 |  |  |  |  | Uitenhage (Erf 10470) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
117 |  |  |  |  | Uitenhage (Erf 12171) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
118 |  |  |  |  | Uitenhage (Erf 3179) | [14 empty] | Approved |  |  |  | No | Draft GP | [8 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
119 |  |  |  |  | Uitenhage (Erf 18613) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
120 |  |  |  |  | Uitenhage (Erf 1754) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
121 |  |  |  |  | Uitenhage (Erf 7927) | [33 empty] | New development. No community issues yet.
122 |  |  |  |  | Vaastrap | [33 empty] | Social instability. Current layout cannont accommodate all households.
123 |  |  |  |  | Moegesukkel (Uitenhage) | [33 empty] | Instability due to challenges of the servicability and availability of land.
124 |  |  |  |  | Moegesukkel (Bethelsdorp) | [33 empty] | Forms part of Bethelsdorp Ext 32, 34 & 36 project. Most people relocated.
125 |  |  |  |  | Edongweni | [33 empty] | Not developable as part of FST Report due to areas falling in pond areas.
126 |  |  |  |  | Enkuthazweni | [33 empty] | Not developable as part of FST Report due to areas falling in pond areas.
127 |  |  |  |  | Endulwini | [33 empty] | Not developable as part of FST Report due to areas falling in pond areas.
128 |  |  |  |  | Chris Hani (New Brighton Tipsite) | [33 empty] | Relocation project. Community resisted relocations.
129 |  |  |  |  | Ramaphosa (New Brighton) | [33 empty] | Relocation project. Community resisted relocations.
130 |  |  |  |  | Mayibuye | [33 empty] | Social instability.
131 |  |  |  |  | Silvertown Powerstation (Tip site) | [33 empty] | Relocation project. Community resisted relocations.
132 |  |  |  |  | Ngxazula (Uitenhage) | [33 empty] | Community instability due to demand for service delivery.
133 |  |  |  |  | Kleinskool Area K | [33 empty] | Small portion left out.
134 |  |  |  |  | Riemvaasmak | [33 empty] | Community residing on private land.
135 |  |  |  |  | Talliban | [33 empty] | Relocations project.
136 |  |  |  |  | Powerline NU8 | [33 empty] | Relocations project.
137 |  |  |  |  | Hlalani NU8 | [33 empty] | Relocations project.
138 |  |  |  |  | Walmwer Area N | [33 empty] | Forms part of Walmer Development.
139 |  |  |  |  | Westville | [33 empty] | Frequent community unrest demanding service delivery
140 |  |  |  |  | Creeky Valley
141 |  |  |  |  | James Mjo
142 |  |  |  |  | Moe Valley
143 |  |  |  |  | Joe Modise (Resevouir) | [33 empty] | No developable due to environmental issues
144 |  |  |  |  | Boo Plaas
Note on A1: temp:
Note on H4: temp: Provincial Department Of Human Settlements (PDOHS)
Note on H18: temp: Urban Settlement Development Grant (USGD)
Note on AJ49: nbonkolo: Stage 2 start date
Note on AJ57: nbonkolo: Stage 2 start date
Note on H65: temp: Urban Settlement Development Grant (USGD)