## Cover
ANNEXURE "M"
URBAN SETTLEMENTS
DEVELOPMENT GRANT
PLAN

## 2019-20 USDG Plan
NELSON MANDELA BAY MUNICIPALITY
URBAN SETTLEMENTS DEVELOPMENT GRANT PLAN 2019/20
Project Name | Overall Financial Target for 2019/20 as per | Overall Financial Target for 2018/19 as per | Overall Non financial Target for 2019/20 as per the | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 3rd Quarter | 3rd Quarter | 4th Quarter | 4th Quarter
| SDBIP-USDG REVISED | SDBIP-USDG | SDBIP-USDG | Planned Financial -USDG | Planned Non financial - USDG | Planned Financial -USDG | Planned non Financial-USDG | Planned Financial -USDG | Planned non Financial-USDG | Planned Financial output | Planned Non Financial | 3% allocation | BUDGET EXCL 3% | BUDGET EXCL VAT
WATER AND SANITATION
Provision of bulk water services for the upgrading of informal settlements | 189750000 |  | 2000 | 18975000 | 400 | 75900000 | 700 | 132825000 | 1200 | 189750000 | 2000
Provision of bulk sanitation services (Capital) for the upgrading of informal settlements | 300000000 |  |  | 30000000 |  | 120000000 |  | 210000000 |  | 300000000
Provision of bulk sanitation services (Operating) for the upgrading of informal settlements | 38920526 |  |  | 3892052.6 |  | 15568210.4 |  | 27244368.2 |  | 38920526 |  | 1167615.78 | 37752910.22 | 32828617.5826
ROADS AND STORMWATER
Tarring of gravel roads | 106950000 | 91200000 | 11 km | 10695000 | 0 km | 42780000 | 0 km | 74865000 | 5 km | 106950000 | 11 km | 3208500 | 103741500 | 90210000
| 0 |  |  |  | (appoint-ment of contractors and site preparation) |  | (box cut and layer works) |  |  | 0
HUMAN SETTLEMENTS
Land acquisition | 30000000 |  | 1 parcel of land | N/A | N/A | N/A | N/A | 30000000 | 1 parcel of land | 30000000 | 1 parcel of land
Servicing of sites (water, sanitation, basic roads) Capital | 200722832 | 230722832 | 2000 | 20072283.2 | 400 | 80289132.8 | 700 | 140505982.4 | 1200 | 200722832 | 2000
| 0 | [8 empty] | 0
Operating Budget | 29270550 | 259993382 | Tender process | 2927055 | Appointment of professional resource team | 11708220 | Implementation and supports i.t.o. capacity | 20489385 | Implementation and supports i.t.o. capacity | 29270550 | Implementation and supports i.t.o. capacity | 878116.5 | 28392433.5 | 24689072.6087
| 0 | [8 empty] | 0
HEALTH AND SOCIAL DEVELOPMENT
Development of Public Open Spaces | 15871092 |  | 9 Public Open Spaces | 1587109.2 | 0 | 6348436.8 | 3 Public Open Spaces | 11109764.4 | 6 Public Open Spaces | 15871092 | 9 Public Open Spaces | 476132.76 | 15394959.24 | 13386921.0783
| 0 |  |  |  | (Prioritisation of sites and procurement)
Development of Cemeteries | 9200000 |  | 2 Cemeteries | 920000 | 0 | 3680000 | 20% completion | 6440000 | 50% completion | 9200000 | 2 Cemeteries | 276000 | 8924000 | 7760000
| 0 |  |  |  | (Prioritisation of sites and procurement)
ENERGY
Public lighting | 9000000 | 9400000 | 470 installations 210 retrofitted | 900000 | 47 installations | 3600000 | 188 installations | 6300000 | 329 installations | 9000000 | 470 installation | 270000 | 8730000 | 7591304.3478
(Area and residential lighting) | 0 |  |  |  | 21 retrofitted |  | 84 retrofitted |  | 147 retrofitted |  | 210 retrofitted
MV&HV Switchgear replacements | 8000000 | 2000000 | 4 substations | 800000 | 1 substation | 3200000 | 2 substations | 5600000 | 3 substations | 8000000 | 4 substations
0
Refurbishment of power transformers | 6000000 |  | 8 Transformers | 600000 | 1 Transformer | 2400000 | 4 Transformers | 4200000 | 6 Transformers | 6000000 | 8 Transformers
Electrification and lighting of subsidised housing areas | 32000000 |  | 1 297 connections | 3200000 | 182 connections | 12800000 | 571 connections | 22400000 | 1 019 connections | 32000000 | 1 297 connections | 960000 | 31040000 | 26991304.3478
| 975685000 | [10 empty] | 7236365.04 |  | 203457219.9652
NOTE 1: FIGURES ARE INCLUSIVE OF VAT |  | -975685000
NOTE 2: REFER TO ANNEXURES FOR DETAIL ON WARDS, COORDINATES, ETC.

## UISP Grant Window =R193 Million
Project description | Settlement Name and description | Overall Target for 2018/19 as per the | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 3rd Quarter | 3rd Quarter | 4th Quarter | 4th Quarter | Geographic Information System (GIS) coordinates of settlements name | Project institutional arangements | Notes | 3% community/social facilitation | Number of households provided with secure tenure | Number of Households provided with individual municipal engineering services (water services, sanitation solutions and electricity – grid and non-grid)
|  | SDBIP-USDG | Planned non-financial target | Planned financial target | Planned non-financial target | Planned financial target | Planned non-financial target | Planned financial target | Planned non-financial target | Planned financial target
|  |  | as per SDBIP - USDG | as per SDBIP | as per SDBIP - USDG | as per SDBIP -USDG | as per SDBIP - USDG | as per SDBIP -USDG | as per SDBIP - USDG | as per SDBIP -USDG
* attach the following documents to this Plan. 1. municipality-wide informal settlements upgrading strategy. 2. Sustainable livelihood Immplementation Plan 3. Support Plan, 4. Risk Management Plan
OutPut 1: Projects with Approved individual informal settlements upgrading plans utilising the National Upgrading Support Programme (NUSP)
Finalizing Projects linked to NUSP as part of internal reticulation services
OutPut 2: Projects with Social Compacts concluded with communities and/or community resource organizations outlining their role in the upgrading process
Walmer Development Providing Sites for Walmer PHP HSDG project
Informal settlements provided with interim and permanent municipal engineering services (public lighting, roads, storm water, refuse removal and bulk connections for water, sanitation and electricity)
Internal Services
Servicing of sites (water, sanitation, basic roads) Capital | Annexure 1 & 4
|  | 2000 | 400 | 20072283.2 | 700 | 80289132.8 | 1200 | 140505982.4 | 2000 | 200722832 | Refer Annexure |  |  |  |  | 2000
Bulk Services
Provision of bulk water services for the upgrading of informal settlements | Annexure 2 | 2000 | 400 | 18975000 | 700 | 75900000 | 1200 | 132825000 | 2000 | 189750000 | Refer Annexure |  |  |  |  | 2000
Provision of bulk sanitation services (Capital) for the upgrading of informal settlements | Annexure 3 | 2000 | 400 | 30000000 | 700 | 120000000 | 1200 | 210000000 | 2000 | 300000000 | Refer Annexure |  |  |  |  | 2000
Provision of bulk sanitation services (Operating) for the upgrading of informal settlements | Annexure 3 | 2000 | 400 | 3892052.6 | 700 | 15568210.4 | 1200 | 27244368.2 | 2000 | 38920526 | Refer Annexure |  |  |  |  | 2000
Development of Public Open Spaces | Annexure 5 | 9 Public Open Spaces | 0 | 1587109.2 | 3 Public Open Spaces | 6348436.8 | 6 Public Open Spaces | 11109764.4 | 9 Public Open Spaces | 15871092 | Refer Annexure
(Prioritisation of sites and procurement)
Public lighting | Annexure 6 | 470 installations 210 retrofitted | 47 installations 21 retrofitted | 900000 | 188 installations 84 retrofitted | 3600000 | 329 installations 147 retrofitted | 6300000 | 470 installations 210 retrofitted | 9400000 | Refer Annexure
754664450

## Annex 1 - Human Settlements
HUMAN SETTLEMENTS
Service: | Servicing of sites | Backlogs: | 38845
Ward and Geographical Locations
Project Title | Items | Ward Number | GPS X Co-ordinates | GPS Y Co-ordinates
KwaNobuhle Area 11 | Roadworks | 45 | +37 43 063.58 | -32 751.68
| Stormwater | 45 | +37 43 063.58 | -32 751.68
| Water | 45 | +37 43 063.58 | -32 751.68
| Sewer | 45 | +37 43 063.58 | -32 751.68
Jachtvlakte HS (Chatty 11-14) | Roadworks | 41 | +37 44 624.38 | -39 684.35
| Stormwater | 41 | +37 44 624.38 | -39 684.35
| Water | 41 | +37 44 624.38 | -39 684.35
| Sewer | 41 | +37 44 624.38 | -39 684.35
Motherwell Development | Roadworks | 54 | +37 40 166.61 | -52 883.31
| Stormwater | 54 | +37 40 166.61 | -52 883.31
| Water | 54 | +37 40 166.61 | -52 883.31
| Sewer | 54 | +37 40 166.61 | -52 883.31
Khayamnandi Extension | Roadworks | 41 | +37 43 358.75 | -43 902.85
| Stormwater | 41 | +37 43 358.75 | -43 902.85
| Water | 41 | +37 43 358.75 | -43 902.85
| Sewer | 41 | +37 43 358.75 | -43 902.85
Seaview | Roadworks | 40 | +37 64 487.13 | -32 537.03
| Stormwater | 40 | +37 64 487.13 | -32 537.03
| Water | 40 | +37 64 487.13 | -32 537.03
| Sewer | 40 | +37 64 487.13 | -32 537.03
Bethelsdorp Ext 32, 34 & 36 | Roadworks | 37 | +37 48 401.89 | -46 981.58
| Stormwater | 37 | +37 48 401.89 | -46 981.58
| Water | 37 | +37 48 401.89 | -46 981.58
| Sewer | 37 | +37 48 401.89 | -46 981.58
Missionvale Garden Lots | Roadworks | 31 | +37 50 644.27 | -50 728.29
| Stormwater | 31 | +37 50 644.27 | -50 728.29
| Water | 31 | +37 50 644.27 | -50 728.29
| Sewer | 31 | +37 50 644.27 | -50 728.29
Ekuphumleni | Roadworks | 19 | +37 50 876.51 | -55 297.12
| Stormwater | 19 | +37 50 876.51 | -55 297.12
| Water | 19 | +37 50 876.51 | -55 297.12
| Sewer | 19 | +37 50 876.51 | -55 297.12
Malabar Ext 6 Phase 2: Area 1 | Roadworks | 12 | +37 54 322.43 | -49 948.08
| Stormwater | 12 | +37 54 322.43 | -49 948.08
| Water | 12 | +37 54 322.43 | -49 948.08
| Sewer | 12 | +37 54 322.43 | -49 948.08
Walmer Development | Roadworks | 4 | +37 62 354.98 | -550215.85
| Stormwater | 4 | +37 62 354.98 | -550215.85
| Water | 4 | +37 62 354.98 | -550215.85
| Sewer | 4 | +37 62 354.98 | -550215.85

## Annex 2 - Water
INFRASTRUCTURE AND ENGINEERING - WATER SERVICES
Ward and Geographical Locations 2018/19
Project ID | Project Title | Summary / Description of Project | Ward Number | GPS X Co-ordinates | GPS Y Co-ordinates
959 - Levies
19990184 | Reservoir Fencing | Fencing at reservoirs | Support Services | 38311 | -3757955
20042881 | Office Accommodation: Water | Regionalisation: Water | Support Services | 57079 | -3759083
20070161 | Coegakop Wellfield and Water Treatment Works (Groundwater) | Groundwater Investigation | Support Services | 56723 | -3738790
20070160 | Purchase New Vehicles | Procurement of vehicles | Support Services | 55690 | -3757876
0
951 - USDG
19930320 | Improvements to System - General | Improvements to System - General | Support Services | Metro Wide | Metro Wide
19950866 | Cathodic Protection of Steel Pipelines | Cathodic Protection of Steel Pipelines | Support Services | 50526 | -3741114
19960156 | Elandsjagt - Upgrade to Restore Capacity | Elandsjagt - Upgrade to Restore Capacity | Support Services | -34125 | -3771528
19990185 | Rehabilitation of Reservoirs | Rehabilitation of Reservoirs | Support Services | 38311 | -3757955
20000037 | Loerie Treatment Works: Rehabilitation | Loerie Treatment Works: Rehabilitation | Support Services | 3515 | -3749053
20000051 | Installation of Zone Water meters | Installation of Zone Water meters | Support Services | Metro Wide | Metro Wide
20010307 | Upgrade of Groendal Water Treatment Works | Upgrade of Groendal Water Treatment Works | 45 & 49 | 35284 | -3736174
20030295 | Construction of Amanzi Reservoir and Pipeline | Construction of Amanzi Reservoir and Pipeline | 53, 54 & 56 | 46848 | -3737936
20030511 | Seaview Bulk Water | Seaview Bulk Water | 40 | 33526 | -3763919
20030512 | St Albans Bulk Water | St Albans Bulk Water | 40 | 31941 | -3753847
20030601 | Construction of a 1,0 Ml reclaimed effluent reservoir: Uitenhage | Construction of a 1,0 Ml reclaimed effluent reservoir: Uitenhage | 47, 48, 49 & 50 | 39458 | -3737637
20042883 | Augment Older Dams Pipelines | Augment Older Dams Pipelines | Support Services | 21440 | -3742087
20042889 | Linton: Additional treatment facility | Linton: Additional treatment facility | 9 | 47281 | -3757673
20050097 | Nooitgedagt / Coega Low Level Scheme | Nooitgedagt / Coega Low Level Scheme | Support Services | 59265 | -3711668
20050106 | Seaview Pump Station: Upgrade | Seaview Pump Station: Upgrade | 40 | 33526 | -3763919
20060080 | Upgrading of Churchill Water Treatment Works | Upgrading of Churchill Water Treatment Works | Support Services | 35313 | -3736184
20060081 | Coega Reclaimed Effluent Scheme | Coega Reclaimed Effluent Scheme | 60 | 57179 | -3750443
20060082 | Upgrading of Springs Water Treatment Works | Upgrading of Springs Water Treatment Works | 51 | 40654 | -3730451
20060083 | Rudimentary Service: Water | Rudimentary Service: Water | Support Services | 55922 | -3739694
20070152 | Access Roads: Upgrade | Access Roads: Upgrade | Support Services | 44210 | -3749876
20070157 | Telemetry Systems: Upgrade | Telemetry Systems: Upgrade | Support Services | 51878 | -3739436
20070161 | Coegakop Wellfield and Water Treatment Works (Groundwater) | Groundwater Investigation | Support Services | 56723 | -3738790
20070162 | Desalination Augmentation | Desalination Augmentation |  | 52034 | -3768046
20080048 | Jagtvlakte: Bulk Water Supply Pipeline | Jagtvlakte: Bulk Water Supply Pipeline | 40 | 39775 | -3743420
20080087 | Rehabilitation of Pipe Bridges | Rehabilitation of Pipe Bridges | Support Services | 1483 | -3756029
20080088 | Bulk Water Metering and Control | Bulk Water Metering and Control | Support Services | Metro Wide | Metro Wide
20080090 | Govan Mbeki Midblock Mains | New water mains installation | 33 | 49600 | -3748020
20080091 | Helenvale Urban Renewal Programme | New water mains installation | 13 | 50703 | -3753465
20080093 | Water Service Maintenance Backlogs: Pump Stations | Water Service Maintenance Backlogs: Pump Stations | Support Services | 39050 | -3737797
20080094 | Water Service Maintenance Backlog: Dams | Water Service Maintenance Backlog: Dams | Support Services | -46783 | -3763861
20080144 | Kwanobuhle: Upgrading of water reticulation | Kwanobuhle: Upgrading of water reticulation | 42, 44, 45, 46 & 47 | 36366 | -3745449
20100034 | Balmoral Reservoir and Bulk Pipeline | Balmoral Reservoir and Bulk Pipeline | 40 | 44407 | -3738115
20120085 | Kwanobuhle Reservoir Link Watermain | Kwanobuhle Reservoir Link Watermain | 40 & 41 | 38133 | -3746791
20162356 | Advanced Meter Infrastructure - Water | Various Non Revenue Water Interventions | Support Services | Metro Wide | Metro Wide
20182414 | Groundwater: Drought Intervention: Drilling of Boreholes |  |  | 55886 | -3759826
20182415 | 1412:Loerie Water Treatment Works:Rehab New Contract |  |  | 3515 | -3749053
20182416 | 1412:Seaview Water Pump Station:Upgrade WIP |  | 40 | 33526 | -3763919
20182419 | 1412:Nooitgedagt/CoegaLowLevel Scheme WTW PH2 Mech&Elec Equipment |  |  | 59265 | -3711668

## Annex 3 - Sanitation
INFRASTRUCTURE AND ENGINEERING - SANITATION SERVICES
Ward and Geographical Locations 2018/19
Project ID | Project Title | Summary / Description of Project | Ward Number | GPS X Co-ordinates | GPS Y Co-ordinates
959 - Levies
19980344 | Replacement of Sewerage Collection Vehicles & Equipment | Procurement of replacement vehicles | Support Services | Metro Wide | Metro Wide
20042918 | Office Accommodation : Sanitation | Sewerage Depots and offices in the Metro require to be upgraded and modified to function as required. | Support Services | Metro Wide | Metro Wide
20070156 | Fishwater Flats WWTW Upgrade | Upgrading WWTW | Support Services | Metro Wide | Metro Wide
951 - USDG
19930112 | Sewer Replacement and Relining | Relining of Sewers that have corroded or require upsizing | Support Services | Metro Wide | Metro Wide
19940098 | Improvements to Sewerage System | To improve the Sewerage System | Support Services | Metro Wide | Metro Wide
19960525 | Chatty Valley Collector Sewer Stage 1 (nodes 20 -24) | Installation of bulk sewerage infrastructure | 33 | 25.5381 | -33.8558
19980348 | Paapenkuils Main Sewers Augmentation | Installation of bulk sewerage infrastructure | 12,40 | 25.4625 | -33.9235
19990130 | Telemetry - Pump Stations | Providing radio links to a central control room to monitor the functioning of the pump stations | Support Services | Metro Wide | Metro Wide
20030030 | Lorraine - Bulk Sewerage Augmentation | Installation of bulk sewerage infrastructure | 1, 6, 8 & 39 | 2846486.194 | -3783645.646
20030034 | Markman - Replace 600mm Sewer | Replacement and upsizing of Badly corroded pipeline and manholes | 16 | 25.6266 | -33.8643
20030167 | Rockland PHB Housing Project: Wastewater Treatment Works | Upgrading WWTW | 40 | 25.2906 | -33.8563
20030182 | Upgrade Despatch Reclamation Works | Upgrading WWTW | 53 | 25.4951 | -33.7991
20030405 | Witteklip Bulk Sewerage | To provide bulk sewerage infrastructure to the area | 40 | 25.2575 | -33.9031
20030407 | Seaview Bulk Sewer | To provide bulk sewerage infrastructure to the area | 40 | 25.3545 | -34.0055
20030672 | Sanitation Services: Rehabilitation of Sewer Pipes | Repairs/replacement of badly corroded sewers and manholes | Support Services | Metro Wide | Metro Wide
20050064 | Augment Collector Sewer for Walmer Heights and Mt Pleasant | Augmentation of existing sewer to provide additional capacity in system for new developments | 1 & 4 | 25.575880 | -33.9997
20050088 | Improve access roads | Improve access roads to WWTW sites | Support Services | Metro Wide | Metro Wide
20050105 | Sewer Protection works for collector sewers | Sewer protection works for collector sewers from stormwater errosion | Support Services | Metro Wide | Metro Wide
20050247 | Rudimentary Services: Sanitation | The provision of basic sanitation services | Support Services | Metro Wide | Metro Wide
20050248 | Bucket Eradication Programme | The provision of basic sanitation services | Support Services | Metro Wide | Metro Wide
20050250 | Driftsands WWTW Phase 3 extension | Upgrading WWTW | 1 | 25.602524 | -34.0161
20060075 | Cape Receife WWTW : Upgrade | Upgrading WWTW | 1 | 2859457.572 | -3786596.468
20060102 | Colchester - Bulk Sewerage Infrastructure & WWTW | Installation of bulk sewerage infrastructure and WWTW | 53 | 25.8076 | -33.6929
20060103 | Jagtvlakte Bulk Sewerage | Installation of bulk sewerage infrastructure | 40, 41 & 46 | 25.4122 | -33.7856
20060106 | Motherwell North Bulk Sewerage | Installation of bulk sewerage infrastructure | 53, 54 & 56 | 25.5925 | -33.7701
20060107 | Motherwell/Coega WWTW and Outfall Sewer | Installation of bulk sewerage infrastructure | 53 & 56 | 25.5925 | -33.7701
20060177 | Driftsands Collector Sewer - Augmentation Phase 1 | Augmentation of existing sewer to provide additional capacity in system for new developments | 1 & 4 | 25.6003 | -34.0135
20060178 | Sanitation Services: Rehabilitation of Pump Stations | Maintenance work required at pump stations to keep them operating safely and at their designed capacity | Support Services | Metro Wide | Metro Wide
20070143 | Rehabilitation of Kwazakhele Collector Sewer | Rehabilitation of badly corroded pipeline | 16 | 25.6163 | -33.8817
20070144 | Kwanobuhle WWTW : Upgrading | Refurbishment of WWTW | 46
20070147 | Kelvin Jones WWTW: Upgrade | Upgrading WWTW | 48 | 25.4262 | -33.7816
20070153 | Brickfields: Upgrade | Upgrading WWTW | 60 | 25.610421 | -33.8303
20070156 | Fishwater Flats WWTW Upgrade | Upgrading WWTW | Support Services | 25.6206 | -33.8811
20080136 | TEI: Sampling Stations | Construction of trade effluent sampling stations to monitor the legal requirements of raw sewage in the system | Support Services | Metro Wide | Metro Wide
20080138 | Kwanobuhle: Upgrading of sewer reticulation | Upgrading of sewers | 42, 43, 44, 45, 46 & 47 | 25.399 | -33.807
20110054 | Motherwell Main Sewer Upgrade | Installation of bulk sewerage infrastructure | 56 & 57 | 25.6083 | -33.8167
20110056 | Swartkops Low Level Collector Sewer Upgrade | Installation of bulk sewerage infrastructure | 18, 19, 21 & 26 | 25.596 | -33.8685
20110066 | Bulk Sewers Joe Slovo, Mandelaville, Allenridge West UIT | Upgrading of Bulk Sewers | 48, 49 & 50 | 25.3845 | -33.7436
20110067 | Industrial Site (Airport Valley) - Bulk Sewer | Installation of bulk sewerage infrastructure | 4 | 25.5929 | -33.9852
20182404 | 1411:Fishwater Flats WWTW: Medium Voltage Network Phase 2 |  | Support Services | 25.6206 | -33.8811
20182409 | Fishwater Flats WWTW: Sludge Stabilisation |  | Support Services | 25.6206 | -33.8811
20182410 | Driftsands WWTW : SCM16-95/C |  | 1 | 25.602524 | -34.0161
20182411 | Driftsands Collector Sewer - Augmentation - Phase 2 |  | 1&4 | 25.6003 | -34.0135
20182418 | 1411:Augment Collector Sewer Walmer Heights |  | 1&4 | 25.575880 | -33.9997
20182431 | Fishwater Flats WWTW: Grit and Sludge Treatment Facility |  | Support Services | 25.6206 | -33.8811
20182540 | Fitzpatrick Pump-station - New | Construction of new sewer pumpstation to provide additonal capacity to system | 48
| Total 959 - Levies | 6500000
| Total 951 - USDG | 303360526
| Total | 309860526

## Annex 4 - Roads
INFRASTRUCTURE AND ENGINEERING - ROADS
SERVICE: Tarring of Gravel Roads
BACKLOG: +- 600 KM
CLUSTER | WARDS | Coordinates
A | 52 | -33.482742, 25.283505
| 53 | -33.473025, 25.363477
56
| 60 | -33.492407, 25.38348
B | 1
| 40 | -33.855667, 25.291065
C | 23 | -33.810489; 25.609551
| 54 | -33.774557; 25.584608
| 55 | -33.795649; 25.573917
| 56 | -33.799248; 25.606840
| 57 | -33.811292; 25.575556
| 58 | -33.806898; 25.578929
| 59 | -33.813849; 25.578721
D | 14 | -33.9007, 25.5977
| 15 | -33.8973, 25.6012
16
| 17 | -33.8951, 25.5893
| 18 | -33.8930, 25.5877
19
20
| 21 | -33.8753, 25.5849
22
| 24 | -33.8632, 25.5738
25
E | 26 | -33.862689, 25.571534
| 27 | -33.858196, 25.559170
| 28 | -33.856796, 25.550010
| 30 | -33.855694, 25.543233
F | 33 | -33.8582777, 25.5230792
| 36 | -33.8695483, 25.5463747
| 37 | -33.8545985, 25.5025903
| 41 | -33.8320832, 25.519039
G | 4 | -33 992898, 25.585311
6
7
8
10
11
12
13
| 29 | -33 855984, 25.467676
31
32
34
| 38 | -33 868912, 25.474233
H | 42 | 33°50'09.3"S 25°23'19.7"E
43
| 44 | 33°49'27.5"S 25°24'06.6"E
| 45 | 33°48'57.3"S 25°22'00.1"E
| 46 | 33°47'36.4"S 25°23'51.0"E
| 50 | 33°44'28.3"S 25°23'32.2"E
| 51 | 33°46'13.0"S 25°25'49.8"E
| 49 | 33°43'48.8"S 25°23'01.7"E
| 47 | 33°47'58.0"S 25°22'51.1"E
| 48 | 33°45'00.7"S 25°23'09.9"E

## Annex 5 - Public Health
PUBLIC HEALTH
SERVICE: | Upgrading/development of Public Open Spaces and Cemeteries
PROJECT ID | PROJECT DESCRIPTION | COORDINATES |  | BENEFITTING WARD(S)
20010362 | Upgrade and Development of Public Open Spaces | 25.4985 | -33.9861 | 8
20010362 | Upgrade and Development of Public Open Spaces | 25.5917 | -33.8798 | 19
20010362 | Upgrade and Development of Public Open Spaces | 25.5912 | -33.8744 | 21
20010362 | Upgrade and Development of Public Open Spaces | 25.5833 | -33.8686 | 22
20010362 | Upgrade and Development of Public Open Spaces | 25.5473 | -33.8594 | 28
20010362 | Upgrade and Development of Public Open Spaces | 25.5035 | -33.8347 | 36
20010362 | Upgrade and Development of Public Open Spaces | 25.3883 | -33.8228 | 44
20010362 | Upgrade and Development of Public Open Spaces | 25.3945 | -33.7474 | 50
20010362 | Upgrade and Development of Public Open Spaces | 25.5831 | -33.7946 | 55
20120045 | Papenkuils Cemetery Fencing | 25.5664 | -33.9171 | 11
20120045 | Russel Road Cemetery | 25.615 | -33.9605 | 5

## Annex 6 - Electricity
ELECTRICITY AND ENERGY
SERVICE: | Electricity and Energy
PROJECT ID | PROJECT DESCRIPTION | COORDINATES |  | BENEFITTING WARD(S)
19930283 | Public Lighting | -33 0 47" 22.37' South | 250 34" 7. 90' East | 54
|  | -33 0 54" 55.23' South | 250 32" 17.86' East | 12
|  | -33° 52" 58.91' South | 25° 35" 53.36' East | 19
|  | -33° 49" 12.86 ' South | 25° 21" 18.49 ' East | 45
|  | -33° 50" 12.52 ' South | 25° 25" 36.13 ' East | 29
|  | -33 0 49" 3.61' South | 250 29" 0.37' East | 41
20042989 | MV & HV Switchgear Relacement
| Winterhoek park Bloemendal Motherwell South Motherwell West | -33.75397 -33.863913 -33.821686 -33.807456 | 25.431496 25.485092 25.589498 25.586326 | 99
20150028 | Refurbishment of Power Transfrormers
| Loerie Pump Station Diaz Rd Tfr 3 & 4 Struandale Tfr 11, 12 & 13 Mount Rd Tfr 24 | -33.869601 -33.937789 -33.890401 -33.945725 | 25.040347 25.582792 25.568418 25.601893 | 99
19930264 | Electrification of State Subsidised Housing Areas
| Motherwell NU 30, Phase 2 | 33 0 47" 22.37' South | 250 34" 7. 90' East | 54
| Walmer Airport Valley, Sec A - On going | 33° 59" 5.99 ' South | 25° 35" 49.06 ' East | 4
| Malabar Ext 6, Phase 2 (Sub Phase 1) | 33 0 54" 55.23' South | 250 32" 17.86' East | 12
| Ekuphumleni | 33° 52" 58.91' South | 25° 35" 53.36' East | 19
| Red Location, Phase 2 | 33 0 49" 33.12' South | 250 28" 46. 55' East | 15
| Chatty Military Veterans - Remainder | 33° 50" 25.63 ' South | 25° 28" 2.46 ' East | 29
| KwaNobuhle Area 11, Phase 2 (Invasion) | 33° 49" 12.86 ' South | 25° 21" 18.49 ' East | 45
| Chatty Jachvlakte, Housing Phase 5B (Invasion) | 33° 50" 12.52 ' South | 25° 25" 36.13 ' East | 29
| Joe Slovo West, Ext 4000 - Remainder | 33 0 49" 3.61' South | 250 29" 0.37' East | 41
| Doornhoek | 33° 45" 32.266 ' South | 25° 22" 38.731 ' East | 48
| New Applications - Access to electricity |  |  | 99