## MTSF
ANNEXURE "H"
NELSON MANDELA BAY MUNICIPALITY
SUMMARY OF 5-YEAR MTSF TARGETS
MTSF TARGET 2019 | National 5 Yr MTSF Target for Metro | Annual MTSF Target | 2014/15 achieved | 2015/16 achieved | 2016/17 Target | 2017/18 Target | 2018/19 Target
750 000 households in informal settlements upgraded to Phase 2 of the Informal Settlements Upgrading Programme | 14 810 | 2 962
Individual Households
Water |  |  | 1 041 | 1 335 | 3 000 | 3 600 | 3 300
Sanitation |  |  | 1 041 | 1 335 | 3 000 | 3 600 | 3 300
Electricity |  |  | 2 215 | 1 945 | 3 000 | 2 000 | 2 500
Shared services (number of households benefiting)
Water |  |  | 24 876 | 24 204 | 22 500 | 21 000 | 19 000
Sanitation |  |  | 24 876 | 24 204 | 22 500 | 21 000 | 19 000
Individual households (serviced sites – not metered) |  |  | 4035 | 3003 | 4000 | 4000 | 4000
Water and Sanitation
Title Deeds:
563 000 for new developments |  |  | 894 | 528 | 1 000 | 1 000 | 1 000
Pre-1994 housing stock |  |  | 163 | 323 | 200 | 200 | 200
Post-1994 housing stock
10 000 of hectares of well-located land

## USDG PLAN
URBAN SETTLEMENTS DEVELOPMENT GRANT PLAN 2017/18
Project Name | Overall Financial Target for 2017/18 | Overall Non financial Target for 2017/18 as per the | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 3rd Quarter | 3rd Quarter | 4th Quarter | 4th Quarter
| SDBIP-USDG | SDBIP-USDG | Planned Financial -USDG | Planned Non financial - USDG | Planned Financial -USDG | Planned non Financial-USDG | Planned Financial -USDG | Planned non Financial-USDG | Planned Financial output | Planned Non Financial
WATER AND SANITATION
Provision of bulk water and sanitation services for the upgrading of informal settlements | 550750000 | 4 000 | R70 mil | 500 | R140 mil | 1 200 | R281 mil | 2 500 | 550750000 | 4 000
ROADS AND STORMWATER
Tarring of gravel roads | 85500000 | 10 km | R8 mil | 0 km | R28 mil | 0 km | R49 mil | 3 km | 85500000 | 10 km
|  |  |  | (appoint-ment of contractors and site preparation) |  | (box cut and layer works)
HUMAN SETTLEMENTS
Servicing of sites | 252711000 | 4 000 | R26 mil | 500 | R67 mil | 1 200 | R134 m | 2 500 | 252711000 | 4 000
(water, sanitation, basic roads)
HEALTH AND SOCIAL DEVELOPMENT
Development of Public Open Spaces | 5700000 | 5 Public Open Spaces | R0 | 0 | R2 mil | 2 Public Open Spaces | R4 mil | 4 Public Open Spaces | 5700000 | 5 Public Open Spaces
(Prioritisation of sites and procurement)
ENERGY
Public lighting | 17100000 | 800 installations | R3 million | 200 | R7 mil | 500 | R11 mil | 600 | 17100000 | 800
(Area and residential lighting) |  |  |  | installations |  | installations |  | installations |  | installations
TOTAL | 911761000