## Nov
HUMAN SETTLEMENTS: DEVELOPMENT & SUPPORT - PROJECT STATUS SUMMARY REPORT - FEBRUARY 2018
GENERAL PROJECT INFO | [10 empty] | TOWNPLANNING |  |  | LAND SURVEYING & PEGGING |  |  | EIA |  | LAND MATTER |  | ENVIRONMENTAL PROCESS |  |  | GENERAL PLAN STATUS |  |  | GEOTECH STATUS |  |  | INFRASTRUCTURE SERVICES |  |  |  | CONSTRUCTION |  |  |  | PROJECT REMARKS
Item |  | Project Manager | Project ID |  | Project Name | GP NUMBER | Funded By: | Ward Number | Project Size (Sites) | Project Type | Date | Consultant | Comments | Date | Consultant | Comments | Date | Consultant | Land Acquisition Status | Land Planning Status | Environmental Impact Assessment | EA Validity | Water Use License (WUL) | GP Approved / not approved | GP Number | Comments | Date | Consultant | Comments | Bulk Infrastructure | Design Consultants | Procurement (Contractor) | Civil Eng. Contractor | Current Project Status | Start Date | End Date | Revised End Date | Comments | Issues | Mitigation Measures | Action By:
1 | COMPLETED PROJECTS | NTOMBI/ ALUNGILE | 20043094 |  | Joe Modise Peace Village Phase 2 | GP 4754/04, 4665/04, 5921/04 | PDOHS | 47 | 429 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 4754/2004, 4665/2004 & 5921/04 |  | Jan 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Kantey & Templer (Pty.) Ltd |  | MMS Developments | Construction of internal services & Top Structures - 100% complete | Aug 2011 | Feb 2013 | April 2013 | Behind Schedule | None | None | None
2 |  |  |  |  | Middle Street Extension |  | USDG | 48 | ±37 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 2260/2002 |  | Sept 2009 | SRK | Available (Ph 1& 2) | Bulks - In place |  |  |  | All internal services (including elec) - complete & site handed over | TBA | TBA | N/A | None | None | None | None
3 |  |  |  |  | Walmer Area O | GP 5290/2008, 2411/2010 | PDOHS | 4 | 437 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 5290/2008, 2411/2010 |  | Aug 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Makhetha Development |  | Simunye Developers | Construction of internal services - in progress (100% complete) | May 2010 | Nov 2010 | June 2013 | Behind Schedule | None | None | None
4 |  |  |  |  | Zosa Street | Draft GP | USDG | 11 | 34 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 208/2013 |  | May 2008 | SRK | Available (Ph 1& 2) | Bulks - In place | SMEC |  |  | Construction of internal services & Top structures - complete | N/A | N/A | N/A | None | None | None | None
5 |  |  | 20110096 | 20110096 | Rosedale Location |  | USDG | [30 empty] | None | None | None | None
6 |  |  |  |  | ● Phase 1 |  |  | 51 | 400 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1296/2012 |  | May 2009 | SRK | Phase 1 & 2 | Bulks - In place | Manong & Associates |  | Izana Cicils | completely serviced | March 2012 | Feb 2013 | May 2014 | Behind Schedule | None | None | None
7 |  |  |  |  | ● Phase 2 |  |  | 51 | 249 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1136/2015 |  | May 2010 | SRK | Phase 1 & 2 | Bulks in place | Manong & Associates |  | TBA | Completely serviced | 2015-02-01 | TBA | N/A |  | People do not want to relocate from serviced area .
8 |  |  | 20130060 |  | Pola Park Extension |  | USDG | 50 | 105 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized | 2017-01-18 | Authorization Pending | No | draft only |  | N/A | N/A | In progress | Bulks - In place | TBA |  | TBA | Completely serviced | TBA | TBA | N/A | None | Testing still needs to be done | None | None
9 |  |  | 20120030 | 20120030 | KwaNobuhle Area 11 |  | USDG | [30 empty] | None | None | None | None
10 |  |  |  |  | ● Phase 1 |  |  | 45 | 350 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | consent issue | May 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Lukhozi Consulting |  | Masakheni | completely serviced | 2013-07-01 | 2015-01-01 | N/A
11 |  |  |  |  | ● Phase 2 |  |  | 45 | 777 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | No | draft only | consent | May 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Lukhozi Consulting |  | Masakheni | Contractor has just commenced with construction of services | 2015-02-01 | TBA
12 |  |  |  |  | Doornhoek |  |  | 48 | 40 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Rapid scan required | Yes | 2381/2001 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | Completely serviced | N/A | N/A | N/A | None | None | None | I&E
13 |  |  |  |  | KwaNobuhle Area 7 Phase 4 |  | USDG | 42 | 244 | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | Yes | Various GP's |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | N/A | N/A | N/A | None | None | None | I&E
14 |  |  |  |  | KwaNobuhle Area 8 Phase 4 |  | USDG | 42 | 266 | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | Yes | Various GP's |  | May 2008 | Bopite | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | N/A | N/A | N/A | None | None | None | I&E
15 |  |  | 20110088 |  | Joe Slovo Uitenhage | Ph1 -GP 865/12 (Ph2 - Draft) | USDG | 48 | 614 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged |  |  | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 865/2012, 1058/2013 |  | Oct 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | BVi Consultants |  | Omega Civils | Completely serviced | May 2012 | April 2013 | 2013-10-01
16 |  |  | 20110094 |  | Mandela & Rolihlahla | Draft GP | USDG | 21 | 218 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 111/2013 & 47/2013 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Worley Parsons |  | Nomaxhosa Construction | Construction of internal services is complete & site handed over | Oct 2011 | Feb 2012 | March 2012 | None | None | None | None
17 |  |  | 20130056 |  | Dikiza Street |  | USDG | 42 | 8 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Rapid scan required | No | draft only | consent issue - with Bhisho (Mr Papu) | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | 2015-07-01 | TBA | N/A | None | None | None | None
18 |  |  |  |  | Ntswahlana Street (Erf. 7916) |  |  | 42 | 10 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 2486/2003 |  | N/A | Bopite | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | 2015-07-01 |  |  |  | None
19 |  |  | 20162364 |  | Kabah Phase 6 (Erf 21647) |  |  | 50 | 54 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Rapid scan required | No | draft only | Council approval for new layout | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | NMBM ( Designed internally) |  | Wavelengths Construction | Project completed , Currently waiting for the liability period to end . | 2015-07-01 | TBA | N/A | None | None | None | None
20 |  |  | 20130038 |  | ERF 8228 KwaNobuhle |  | USDG | 42 | 111 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | No | draft only | few shacks in way-Councillor | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | PDNA |  | TBA | Construction of sevices 100% complete,All the tests passed . | 2015-03-01 | TBA | N/A |  | Termination report still sitting at Legal
49 |  |  | 20162359 |  | Uitenhage (Erf 10015 ,Uitenhage) |  |  | 49 | 12 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | TBA | Construction of internal services is complete |  |  |  |  | None
50 |  |  | 20162363 |  | Rosedale (Erf 12872 , Uitenhage) |  |  | 49 | 30 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | Masiphumelele Trading | Construction of internal services is complete |  |  |  |  | New development. No community issues yet.
21 |  |  | 20130060 |  | Polla Park (Erf 28487, Uitenhage) |  | USDG | 51 | 117 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Bush Clearing - Underway | N/A | N/A | Municipal Owned | Approved | Authorized |  | N/A | No | draft only | ready to lodge GP | N/A | N/A | Not Available | Bulks - In place | ILISO |  | TBA | 80% complete , Constructuction will be complete by the 22nd of August. | 2015-02-01 | TBA | N/A |  | EME's have not been paid
5 |  | RAYNO |  |  |  |  | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | Busy amend layout/GP to avoid construction delay | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services is complete & site handed over | Nov 2012 | April 2013 | May 2013 | None | None | None | None
22 |  |  |  |  | KwaNontshinga |  | USDG | 20 | 105 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1422/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Arcus Gibb Consulting |  | Ascon Trading | Construction of internal services is complete & site handed over |  | Sept 2013 | March 2013 | Behind Schedule | None | Arcuss give to provide the certificates | Consultant (Arcus Gibb)
3 | [5 empty] | Draft GP | USDG | [11 empty] | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 111/2013 & 47/2013 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Worley Parsons |  | Nomaxhosa Construction | Construction of internal services is complete & site handed over | Oct 2011 | Feb 2012 | March 2012 | None | None | None | None
4 | [6 empty] | USDG | [11 empty] | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 2260/2002 |  | Sept 2009 | SRK | Available (Ph 1& 2) | Bulks - In place |  |  |  | All internal services (including elec) - complete & site handed over | TBA | TBA | N/A | None | None | None | None
23 |  |  | 20120042 |  | Sisulu Village Phase 2 (Hlalani Qeqe) |  | USDG | 26 | 18 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 15/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services - 100% complete,ready for top structures | Nov 2012 | April 2013 | May 2013 |  | None | None | None
24 |  |  | 20110090 |  | Roos Street | GP 4271/09 | USDG | 10 | 28 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 4271/2009 |  | May 2008 | SRK | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services is complete & site handed over | Nov 2012 | March 2013 | July 2013 | Behind Schedule | None | None | None
25 |  |  | 20110097 |  | Motherwell High Density |  | USDG | 58 | 109 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | Busy amend layout/GP to avoid construction delay | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services is complete & site handed over | Nov 2012 | April 2013 | May 2013 | None | None | None | None
26 |  |  | 20110092 |  | Missionvale Garden Lots (Phase 1 & 2) |  |  | 32 | 929 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 218/2009, 3478/2011 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Sigodi Marah Martin |  |  | Construction of internal services- 100% complete ¦ Top Structures 100% complete | Aug 2012 | May 2013 | May 2016 | May 2015 | None | May 2017 | May 2018
27 |  |  | 20110092 |  | Missionvale Garden Lots |  | USDG |  |  | Human Settlements Project (Greenfields)
28 |  |  |  |  | ● Phase 3,4 & 5 |  |  | 31 | 1483 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 4459/2009, 5259/09 & 6017/09 |  | N/A | N/A | Available (Ph 1, 2, 3 & 5) |  | EAS |  |  | Construction of internal services- 100% complete ¦ Top Structures 90% complete | Jan 2014 | Jun 2014 | Jun 2016 | None | unblocking of sewer, checking watermeters and internal plumbing of houses. | None | None
29 |  |  | 20120052 |  | Walmer Q Phase 3 |  | USDG | 4 | 188 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | part of G West | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Makhetha Development |  | Power Construction | Construction of internal services - in progress (100% complete) | Oct 2012 | Aprli 2013 |  | On Schedule | None | None | None
56 |  |  | 20120054 |  | Walmer Airport Valley - Section A |  | USDG | 4 | 317 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | No | Draft only | relocation | N/A | N/A | Available (Ph 1 & 2) | Bulks - In place | Makhetha Development Consultants | Section A - Complete | Omega Civils | Construction of internal services- 100% complete | 2015-11-01 | 2016-09-01 | 2017-09-01 | None | None
30 |  |  | 20110095 |  | Red Location |  | USDG | 15 | 172 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 901/2012 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Goba Consulting Eng. |  | SJW | Construction of internal services- 100% complete | May 2013 | Oct 2013 | Jun 2014 |  | None
31 |  | NWABISA | 20110091 |  | Khayamnandi Extension |  | USDG
32 |  |  |  |  | ● Phase 1a & 1b |  | USDG | 41 | 471 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 98/2013, 883/2013 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Masakeni Construction | Construction of internal services - 100% complete | Aug 2012 | Sept 2013 | May 2014 | On Schedule | Awaiting WUL | None | Uhambiso
33 |  |  |  |  | ● Phase 2 |  | USDG | 41 | 1013 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 876/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Civils 2000 | Construction of internal services - 100% complete | Aug 2012 | Sept 2013 | May 2014 | None | None | None | None
34 |  |  |  |  | ● Phase 3 |  |  | 52 | 206 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 16/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place |  |  |  | Construction of internal services - 100% complete | June 2013 | May 2014 | Dec 2014 | None | None | None | None
35 |  |  |  |  | ● Phase 4a |  | USDG | 41 | 358 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1268/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Civils 2000 | Construction of internal services - 100% complete | April 2013 | June 2014 | Dec 2014 | None | None | None | None
36 |  |  |  |  | ● Phase 4b |  |  | 41 | 372 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1268/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Masakeni Construction | Construction of internal services - 100% complete | April 2013 | June 2014 | Dec 2014 | None | None | None | None
37 |  |  | 20130019 |  | Motherwell NU12 |  | USDG | 54 | 350 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Pre - ECA | No | Draft only | With SG | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Hemsley & Mydral |  | Masakeni Construction | Construction of internal services- (100% complete) | March 2013 | July 2013 | July 2014 | None | None | None | None
38 |  |  |  |  | Phase 2 (Qaqawuli) |  |  |  | 491 | Disadvantaged Project Area (In-situ) | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | In-situ Upgrade: Low Income | Municipal Owned | Approved | Authorized - NO EA Required |  |  | No | draft only | relocation | Sep 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | KCS Consultants |  | TBA | Phase 2 - at practical completion stage , left with snags | TBA | TBA | N/A |  | None
39 |  |  | 20110093 |  | Motherwell NU29 |  | USDG | 54 | 3478
40 |  |  |  |  | ● Phase 1 |  |  | 54 | 1335 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 5412/02 & 2404/2002 |  | Feb 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services & Top Structures- 100% complete | Jul 2012 | March 2013 | End March 2013 |  | None | None | None
41 |  |  |  |  | ● Phase 2 Stage 1 |  |  | 54 | 1253 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1097/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services is complete & site handed over
42 |  |  |  |  | ● Phase 2 Stage 2 |  |  | 54 | 890 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 586/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services is complete & site handed over |  | March 2013 | May 2013 | Behind Schedule | None | None | None
43 |  |  |  |  | Motherwell NU30 | Draft GP | USDG | 54 | 2067 |  | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | TBA | [8 empty] | Oct 2009 | SRK |  |  | Goba ¦ Izizwe Consultants |  | Masakheni |  | Mar 2014 | Mar 2015 | N/A | None | Farmer's issues | Department of Agriculture to intervene | None
44 |  |  |  |  | ● Phase 1 |  |  | 54 | 605 | Human Settlements Project (Greenfields) | [8 empty] | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1014/2014 |  | Oct 2010 | SRK | Available (Ph 1& 2) | Bulks - Under Planning |  |  |  | Phase 1 - Construction underway 100% complete |  |  | Nov 2015
45 |  |  |  |  | ● Phase 2 |  |  | 54 | 800 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | RoD available | Yes | 1181/2013 |  | Oct 2010 | SRK | Available (Ph 1& 2) | Bulks - Under Planning |  |  |  | At Practical Completion Stage . Outstanding : Claim from Masakeni & The testing of 200m line . | Jan 2015 | Jan 2017 | N/A |  | None
46 |  |  | 20120060 |  | Masakhane Village |  | USDG | 24 | 125 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Authorized - No WUL required | No | draft only | Consent outstanding (PK) | Sep 2010 | SRK | Available (Ph 1& 2) | Bulks - In place | Eyethu Consultants |  | TBA | RoD and WULA are in place. Construction underway | TBA | TBA | N/A | None | No social issues at this stage | None | None
47 | [6 empty] | USDG
7 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 5412/02 & 2404/2002 |  | Feb 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services & Top Structures- 100% complete | Jul 2012 | March 2013 | End March 2013 |  | None | None | None
8 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 1097/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services is complete & site handed over
9 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 586/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Izizwe Consultants |  | Masakeni Construction | Construction of internal services is complete & site handed over |  | March 2013 | May 2013 | Behind Schedule | None | None | None
10 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 15/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services - 100% complete,ready for top structures | Nov 2012 | April 2013 | May 2013 |  | None | None | None
11 | [5 empty] | GP 4271/09 | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 4271/2009 |  | May 2008 | SRK | Available (Ph 1& 2) | Bulks - In place | SMEC |  | SJW Civils | Construction of internal services is complete & site handed over | Nov 2012 | March 2013 | July 2013 | Behind Schedule | None | None | None
12 | [5 empty] | GP 5290/2008, 2411/2010 | PDOHS |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 5290/2008, 2411/2010 |  | Aug 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Makhetha Development |  | Simunye Developers | Construction of internal services - in progress (100% complete) | May 2010 | Nov 2010 | June 2013 | Behind Schedule | None | None | None
13 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | No | Draft only | part of G West | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Makhetha Development |  | Power Construction | Construction of internal services - in progress (100% complete) | Oct 2012 | Aprli 2013 |  | On Schedule | None | None | None
14 | [5 empty] | Draft GP | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 208/2013 |  | May 2008 | SRK | Available (Ph 1& 2) | Bulks - In place | SMEC |  |  | Construction of internal services & Top structures - complete | N/A | N/A | N/A | None | None | None | None
15 | [5 empty] | Ph1 -GP 865/12 (Ph2 - Draft) | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | [6 empty] | RoD available | Yes | 865/2012, 1058/2013 |  | Oct 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | BVi Consultants |  | Omega Civils | Construction of internal services - in progress (100% complete) | May 2012 | April 2013 | 2013-10-01
16 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 218/2009, 3478/2011 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Sigodi Marah Martin |  |  | Construction of internal services- 100% complete ¦ Top Structures 100% complete | Aug 2012 | May 2013 | May 2016 | May 2015 | None | May 2017 | May 2018
17 | [6 empty] | USDG
18 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 4459/2009, 5259/09 & 6017/09 |  | N/A | N/A | Available (Ph 1, 2, 3 & 5) |  | EAS |  |  | Construction of internal services- 100% complete ¦ Top Structures 90% complete | Jan 2014 | Jun 2014 | Jun 2016 | None | unblocking of sewer, checking watermeters and internal plumbing of houses. | None | None
19 | [6 empty] | USDG
20 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 98/2013, 883/2013 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Masakeni Construction | Construction of internal services - 100% complete | Aug 2012 | Sept 2013 | May 2014 | On Schedule | Awaiting WUL | None | Uhambiso
21 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 876/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Civils 2000 | Construction of internal services - 100% complete | Aug 2012 | Sept 2013 | May 2014 | None | None | None | None
22 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A |  |  |  |  | RoD available | Yes | 16/2015 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place |  |  |  | Construction of internal services - 100% complete | June 2013 | May 2014 | Dec 2014 | None | None | None | None
23 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A |  |  |  |  | RoD available | Yes | 1268/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Civils 2000 | Construction of internal services - 100% complete | April 2013 | June 2014 | Dec 2014 | None | None | None | None
24 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegging - In progress | N/A | N/A |  |  |  |  | RoD available | Yes | 1268/2014 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Uhambiso Consulting |  | Masakeni Construction | Construction of internal services - 100% complete | April 2013 | June 2014 | Dec 2014 | None | None | None | None
25 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | Pre - ECA | No | Draft only | With SG | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Hemsley & Mydral |  | Masakeni Construction | Construction of internal services- (100% complete) | March 2013 | July 2013 | July 2014 | None | None | None | None
26 | [5 empty] | Draft GP | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 905/2012, 919/12, 921/12 & 183/12 |  | Oct 2009 | SRK | Phase 1 & 2 | Bulks - In place | Bosch Stemele Consulting |  | Masakeni Construction | Construction of internal services - (100% complete) | May 2012 | May 2013 | July 2014 | Behind Schedule | None | None | None
27 | [6 empty] | USDG |  |  |  | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  | Environmental Exemption |  | RoD available | Yes | 901/2012 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | Goba Consulting Eng. |  | SJW | Construction of internal services- 100% complete | May 2013 | Oct 2013 | Jun 2014 |  | None
28 | [6 empty] | USDG | [30 empty] | None | None | None | None
29 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A |  |  |  |  | RoD available | Yes | 1296/2012 |  | May 2009 | SRK | Phase 1 & 2 | Bulks - In place | Manong & Associates |  | Izana Cicils | completely serviced | March 2012 | Feb 2013 | May 2014 | Behind Schedule | None | None | None
30 | [6 empty] | USDG | [30 empty] | None | None | None | None
31 | [10 empty] | N/A | N/A | Underway | N/A | N/A | Not Pegged | TBA | TBA |  |  |  |  | RoD available | No | Draft only | consent issue | May 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | Lukhozi Consulting |  | Masakheni | completely serviced | 2013-07-01 | 2015-01-01 | N/A
32 | [10 empty] | N/A | N/A | Available | N/A | N/A | Pegged | TBA | TBA |  |  |  |  | Rapid scan required | Yes | 2381/2001 |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | Completely serviced | N/A | N/A | N/A | None | None | None | I&E
33 | [6 empty] | USDG |  |  |  | N/A | N/A | Not Available | N/A | N/A | Pegged | TBA | TBA |  |  |  |  | RoD available | Yes | Various GP's |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | N/A | N/A | N/A | None | None | None | I&E
34 | [6 empty] | USDG |  |  |  | N/A | N/A | Not Available | N/A | N/A | Pegged | TBA | TBA |  |  |  |  | RoD available | Yes | Various GP's |  | May 2008 | Bopite | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA | completely serviced | N/A | N/A | N/A | None | None | None | I&E
48 | PROJECTS UNDER IMPLEMENTATION | NTOMBI/ ALUNGILE | 20120059 |  | Chatty Jachtvlakte |  | USDG | 41 | ±12000 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approval Pending | Authorized | 2017-09-22 |  | No | nil |  | N/A | N/A | Underway | Bulks - Under Planning | Aurecon |  | Tecni Civils | The contractor has since started with site establishment for HS 5b ,on Wednesday the 2nd of August 2017. | TBA | TBA | N/A | None | HS 5b is under implementation , Budget provision has been made for HS 5b to be implemented by next financial year | None | None
51 |  |  | 20162365 |  | Uitenhage (Erf 12931) |  |  | 49 | 35 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A | Pegged | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | TBA | Sewer and water is 100% complete , I&E to appoint contractor for road construction |  |  |  |  | Might go above the budget , because the earthworks were nor included and the are is steepy nedds to be evened out
52 |  |  | 20162361 |  | McCarthy Land (Erf 6480 , Afghanistan) |  |  | 48 | 43 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A |  | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | TBA | On the way to I&E |  |  |  |  | Land invasion isuues and eviction orders issued.
53 |  |  | 20162360 |  | Uitenhage (Erf 3179) |  |  | 48 | 42 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A |  | TBA | TBA | Municipal Owned | [11 empty] | NMBM ( Designed internally) |  | Masiphumelele Trading | Sewer and water is 100% complete , The contractor is busy roads . |  |  |  |  | New development. No community issues yet.
54 |  |  | 20120030 |  | KwaNobuhle Area 11 |  | USDG | [30 empty] | None | None | None | None
55 |  |  | 20120030 |  | Phase 3a & 3b |  | USDG | 45 | 319 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Not Pegged |  |  | Municipal Owned | Council Approved - COGTA Confirmation Pending | Authorized |  | Authorized | No | nil |  |  |  | Available (Ph1 &2) | Bulks in progress | Lukhozi Consulting |  | TBA | Phase 3a is 66% complete ,Phase 3b also under construction | TBA | TBA | N/A |  | No social issues at this stage
57 |  |  | 20120059 |  | Malabar Ext. 6 Phase 2 |  | USDG | 12 | 671 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Land Surveyor appointed. Phase 1 pegged. Relocation complete for Phase 2. | N/A | N/A | Municipal Owned | Approved | Authorized | 2018-10-02 | Approved | No | nil | Land surveyor busy with draft gp. | N/A | N/A | Available (Ph 1) | Bulks - In place, but upgrading of portions required. | IX Engineers | Phase 1 and Phase 2 complete. | Phase 1 - Raubex Strata | Phase 1 - is currently under construction ,currently at 70 % completion. Phase 2 to be awarded by March 2018. | TBA | 2018-05-01 | N/A | None | Phase 1 progress well with anticipated completion by April 2108. | None | None
58 |  | NWABISA | 20110091 |  | Khayamnandi Extension |  | USDG
59 |  |  |  |  | ● Phase 6 North |  |  | 41 | 402 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A |  |  |  |  | RoD available | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | The scope of work for the contractor has been reduced. A new programme will be submitted by the contractor with the revised completion date. | TBA | TBA | N/A | None | None | None
60 |  |  | 20120053 |  | MK Silvertown 2 Qaqawuli |  | USDG | 16 | [29 empty] | None |  | None | Properties
61 |  |  |  |  | ● Phase 1 (MK Silvertown) |  |  |  | 275 | Disadvantaged Project Area (In-situ) | N/A | N/A | Draft Available | N/A | N/A | Not Pegged | TBA | TBA |  |  |  |  | RoD available | No | draft only | relocation | Sep 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | KCS Consultants |  | TBA | Construction Underway | TBA | TBA | N/A
61 |  |  |  |  | ● Phase 2 (Qaqawuli) |  |  |  | 491 | Disadvantaged Project Area (In-situ) | N/A | N/A | Draft Available | N/A | N/A | Not Pegged | TBA | TBA |  |  |  |  | RoD available | No | draft only | relocation | Sep 2009 | SRK | Available (Ph 1& 2) | Bulks - In place | KCS Consultants |  | TBA | Construction Underway | TBA | TBA | N/A
62 | PROJECTS UNDER PLANNING | NTOMBI/ ALUNGILE | 20120059 |  | Chatty Jachtvlakte |  | USDG | 41 | ±12000 | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approval Pending | Authorized | 2017-09-22 |  | No | nil |  | N/A | N/A | Underway | Bulks - Under Planning | Aurecon |  | Tecni Civils | The contractor has commenced with work on site and the project is under construction. | TBA | TBA | N/A | None | No social issues at this stage | None | None
63 |  |  | 20120030 |  | KwaNobuhle Area 11 |  | USDG | [30 empty] | None | None | None | None
64 |  |  | 20120030 |  | Future Phases 4 & 5 |  | USDG | 45 | TBA | Human Settlements Project (Greenfields) | N/A | N/A | Underway | N/A | N/A | Not Pegged |  |  | Municipal Owned | Council Approved - COGTA Confirmation Pending | Authorized |  | Authorized | No | nil |  |  |  | Available (Ph1 &2) | Bulks in progress | Lukhozi Consulting |  | TBA | Phase 4 curently under evaluation , Phase 5 of the internal services has been budgeted for in the next financial year | TBA | TBA | N/A |  | None
65 |  |  | 20162370 |  | Uitenhage (Erf 818-863) |  | USDG | 51 | 131 | Disadvantaged Project Area (In-situ) | N/A |  |  | N/A | N/A |  | TBA | TBA | Municipal Owned |  |  |  |  | No | nil | [5 empty] | NMBM ( Designed internally) |  | TBA | At preliminary design stage |  |  |  |  | New development. No community issues yet.
66 |  |  |  |  | Witteklip |  | USDG | 40 | 256 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned - Land Ownership Challenged | Approved | Residential Component Authorized; Bulk Component challenged | Residential OK |  | No | nil |  | N/A | N/A | Not Available | Bulks - Under Planning | TBA |  | TBA | Awaiting technical report from Waste Water & Conveyance wrt the type of sanitation to be used. | TBA | TBA | N/A | None | None | None | None
59 |  |  |  |  | Uitenhage (Erf 29669) |  |  | 50 | 19 | Disadvantaged Project Area (In-situ) |  | 29669 | V14B-X-9 | [5 empty] | Municipal Owned | Approved |  |  |  | No | Draft GP | [8 empty] | At preliminary designstage |  |  |  |  | New development. No community issues yet.
67 |  |  |  |  | Uitenhage (Erff 7927) |  |  | 49 | 13 | Disadvantaged Project Area (In-situ) | [8 empty] | Municipal Owned | [14 empty] | At preliminary designstage |  |  |  |  | New development. No community issues yet.
68 |  | RAYNO | 20110094 |  | Mandela Village | Draft GP | USDG | 18 | 71 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Pegged | N/A | N/A | Municipal Owned |  |  |  | RoD available | No | draft only | relocation process | Sept 2008 | SRK | Phase 1 & 2 | Bulks - In place | Worley Parsons |  | Masakeni Construction | Construction of internal services (50% complete) - put on hold (awaiting relocations) | TBA | TBA | N/A | None | Resistance to relocation. Anticipated project completion was in 2010. | None | Social Development
69 |  |  | 20130054 |  | Bethelsdorp (Extension 32, 34 & 36) |  | USDG | 37 | TBA | Human Settlements Project (Greenfields) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned |  |  |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place | Gilgal Development Consultants and Project Managers |  | TBA | Consultants submited Prelim Design Report , Awaiting feedback from DEDEAT to identify which EIA process to be followed. | TBA | TBA | N/A | None | Awaiting feedback from Environmental Management wrt EIA process to be followed. | None | None
70 |  |  | 20120031 |  | Ekuphumleni |  | USDG | 19 | 191 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Portions Pegged. Pegging to be completed. | N/A | N/A | Municipal Owned | Approved | Authorized - NO EA Required | Not applicable | N/A | No | draft only | Relocation process kick-started after delays due to resistance. | N/A | N/A | Available (Ph 1) | Bulks - In place | Arcuss Gibb |  | TBA | Tender cancelled until relocation issues sorted. New procurement to be followed during 2017/18 to appoint contractor in 2018/2019. | TBA | TBA | N/A | None | Relocation kick-started. To start new procurement process for construction to commence in 2018/19. | De-densify existing shacks | Social Development
71 |  |  | 20120048 |  | N2 North [Grogro] |  |  | 39 | ±2000 | Human Settlements Project (Greenfields) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | In Progress | DEDEAT Refusal |  | Awaiting approval | No | nil |  | N/A | N/A | Phase 1 Available | Bulks - Under Planning | UWP/Iliso |  | TBA | DEDEAT refusal of project. Currently busy with appeal process. | TBA | TBA | N/A | None | Project processes stagnant until appeal process concluded | None | None
72 |  |  |  |  | Kalipa |  | USDG | 19 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Approved | Authorized - NO EA Required |  |  | No | nil |  | N/A | N/A | Available (Ph 1& 2) | Bulks - In place | TBA |  | TBA |  | TBA | TBA | N/A | None | No social issues at this stage | None | None
73 |  |  | 20120062 |  | Kuyga Phase 3 |  | USDG | 40 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Land issue¦ Provincial Land | Planning pending appointment of lead consultant | EIA dependent on land acquisitioning |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place |  |  | TBA | Initial project planning stages - Awaiting completion of Bulk Sewer Rising Main.¦ Letter to be submitted to Province for availability of land. | TBA | TBA | N/A | None | Availability of land. | None | None
75 |  |  |  |  | Singaphi |  | USDG | 15 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | To be approved | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized - NO EA Required |  |  | No | nil |  | N/A | N/A | Not Required | Bulks - In place | TBA |  | TBA | To formalize the Town Planning layout | TBA | TBA | N/A | None | None | None | Land Planning
76 |  |  | 20120054 |  | Walmer Gqeberha Developments |  |  | 4 | 3500 | Greenfields and In-situ Developments | [27 empty] | None |  | None | None
77 |  |  | 20120054 |  | Walmer Gqeberha 1948 - section A |  |  | 4 |  | Temporary Relocation Area | N/A | Metroplan | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  |  | No | nil |  | N/A | N/A | Not Available | No Bulks | Makhetha Development Consultants | In progress |  |  | TBA | TBA | N/A |  | Slow Suplly Chain processes.
78 |  |  | 20120054 |  | Walmer Gqeberha 1948 - TRA |  |  | 4 |  | Human Settlements Project (Greenfields) | N/A | Metroplan | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized | 36 mnths from commencement of Phase 2 |  | No | nil |  | N/A | N/A | Not Available | No Bulks | Makhetha Development Consultants |  |  | For Bulk Water Supply, the current contractor will be used to complete the work that was left by the previous contractor. For the Access Road, site establishment has been done and exposing of services. | TBA | TBA | N/A |  | None
79 |  |  | 20120054 |  | Walmer Gqeberha 11305 |  |  | 4 |  | Human Settlements Project (Greenfields) | N/A | Metroplan | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | In Progress | FEIR Pending Authorization |  |  | No | nil |  |  |  | Not Available | To be identified during design phase | Makhetha Development Consultants |  |  |  | TBA | TBA | N/A |  | Awaiting DEDEAT response wrt submission of FEIR.
80 |  |  |  |  | Seaview / Clarendon Marine |  |  | 40 | TBA | Human Settlements Project (Greenfields) | N/A | N/A |  | N/A | N/A | Not Pegged | N/A | N/A | Municipal and PDHOS: Viability of land development challenged by environmental considerations | In Progress/ Currently Suspended pending outcome of technical solution | FEIR Pending Authorization |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - Under Planning | Gilgal Development Consultants and Project Managers |  |  | Lead Consultant appointed. Completed preliminary designs to form part of the FEIR. | TBA | TBA | N/A |  | Awaiting DEDEAT response wrt submission of FEIR.
81 |  | NWABISA |  |  | Khayamnandi Extension |  |  | 205 | 4586 | Human Settlements Project (Greenfields) | [8 empty] | Municipal Owned | Approved | Authorized |  | Authorized
82 |  |  |  |  | Phase 5 |  |  | 41 | 939 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | Procurement process of a contractor is underway | TBA | TBA | N/A | None | None | None
83 |  |  |  |  | Phase 7 |  |  | 41 | 1079 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | Designs under the approval process by I&E | TBA | TBA | N/A | None | None | None
84 |  |  |  |  | Phase 8 |  |  | 41 | 1009 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | No designs as yet | TBA | TBA | N/A | None | None | None
85 |  |  |  |  | Phase 9 |  |  | 41 | 1017 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | No designs as yet | TBA | TBA | N/A
86 |  |  |  |  | Phase 10 |  |  | 41 | 542 | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | N/A | N/A | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | No Bulks | Uhambiso |  | TBA | No designs as yet | TBA | TBA | N/A
87 |  |  | 20120053 |  | MK Silvertown 2 Qaqawuli |  | USDG | 16 | [25 empty] | Phase 1 is complete, phase 2 is 20% complete. The previous contractor has been termintaed due to liquidation of the company and the remaining work will be done under the Qaqawuli contract. |  |  |  | None | None | None | Properties
88 |  |  | 20120061 |  | Motherwell NU31 |  | USDG | 54 | TBA | Human Settlements Project (Greenfields) | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Approved | Authorized |  | Authorized | No | nil |  | N/A | N/A | Available (Ph 1& 2) | Bulk Infrastructure challenges | TBA |  | TBA | Bulk services to be sorted out | TBA | TBA | N/A | None | Farmer's issues | Department of Agriculture to intervene | HS: Development & Support
89 |  |  |  |  | Ramaphosa West |  | USDG | 56 | TBA | Human Settlements Project (Greenfields) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Pending Planning | Rapid scan required |  |  | No | nil |  | May 2008 | Bopite | Available (Ph 1& 2) | Bulks Challenged | TBA |  | TBA | Undergoing SALT process | TBA | TBA | N/A | None | Social instability | None | None
90 |  |  | 20130057 |  | Kleinskool Kliprand |  | USDG | 34 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned and portions private land | Pending Planning | EIA Required |  |  | No | nil |  | N/A | N/A | Not Available | To be finalized during planning process | Gibb |  | TBA | Land acquisition is underway. LOA issued to Consultant to commence with planning process. | TBA | TBA | N/A | None | Portion of community residing on privately-owned land. | None | None
91 |  |  | 20120051 |  | Nkatha Seyisi |  | USDG | 19 | 72 | Disadvantaged Project Area (In-situ) | N/A | N/A | To be approved | N/A | N/A | Not Pegged | TBA | Aurecon | Municipal Owned | Pending Planning | To appoint EAP |  |  | No | nil |  | N/A | N/A | Not Available | Bulks - In place | Gibb |  | TBA | LOA issued to Consultant to start with planning processes.¦ Tender document to be signed | TBA | TBA | N/A | N/A | Awaiting feedback for HIA ¦ Preliminary reports submitted for review ¦ Topographical Survey and Geotechnical Investigation under-way. | None | None
92 |  |  |  |  | Raymond Mhlaba (Buyambo) |  | USDG | 21 | 50 | Disadvantaged Project Area (In-situ) | N/A | N/A | Available | N/A | N/A | Not Pegged | TBA | Aurecon | Municipal Owned | To be confirmed | Authorized | 2014-09-22 |  | No | draft only | Consent required (PK) | N/A | N/A | Not Available | Bulks - In place | AHS |  | TBA | Construction is almost complete, anticipated to finish end of September 2017. | TBA | TBA | N/A | None | No social issues at this stage | None | None
93 |  |  |  |  | Tyinira Endlovini |  | USDG | 57 | TBA | Disadvantaged Project Area (In-situ) | N/A | N/A | Not Available | N/A | N/A | Not Pegged | TBA | TBA | Municipal Owned | Planning pending appointment of lead consultant | Rapid scan required |  |  | No | nil |  | N/A | N/A | Not Available | Bulks Challenged | TBA |  | TBA | Initial project planning stages | TBA | TBA | N/A | None | Social instability | None | None
95 | FUTURE PROJECTS |  |  |  | Allanridge West (Uitenhage) |  |  | 49 | 201 |  |  |  | B-LD 209 | [20 empty] | On the way to I&E |  |  |  |  | Land invasion isuues and eviction orders issued.
96 |  |  |  |  | McCarthy Land (Erf 17585 , Rosedale) |  |  | 49 | 101 |  |  | 17585 | B-LD 209 | [20 empty] | On the way to I&E |  |  |  |  | Land invasion isuues and eviction orders issued.
97 |  |  |  |  | Uitenhage (Erf 26022) | [28 empty] | On the way to I&E |  |  |  |  | New development. No community issues yet.
98 |  |  |  |  | Wintehoek Park | [28 empty] | EIA Issue |  |  |  |  | New development. No community issues yet.
99 |  |  |  |  | Uitenhage (Erf 7939) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
100 |  |  |  |  | Uitenhage (Erf 8061) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
101 |  |  |  |  | Uitenhage (Erf 9498) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
102 |  |  |  |  | Uitenhage (Erf 12591) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
103 |  |  |  |  | Uitenhage (Erf 12592) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
104 |  |  |  |  | Uitenhage (Erf 15154) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
105 |  |  |  |  | Uitenhage (Erf 15831) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
106 |  |  |  |  | Uitenhage (Erf 16015) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
107 |  |  |  |  | Uitenhage (Erf 17547) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
108 |  |  |  |  | Uitenhage (Erf 17639) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
109 |  |  |  |  | Uitenhage (Erf 23247) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
110 |  |  |  |  | Uitenhage (Erf 24078) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
111 |  |  |  |  | Uitenhage (Erf 26020) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
112 |  |  |  |  | Uitenhage (Erf 26022) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
113 |  |  |  |  | Uitenhage (Erf 8043) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
114 |  |  |  |  | Uitenhage (Erf 16040) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
115 |  |  |  |  | Uitenhage (Erf 26848) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
116 |  |  |  |  | Uitenhage (Erf 10470) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
117 |  |  |  |  | Uitenhage (Erf 12171) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
118 |  |  |  |  | Uitenhage (Erf 3179) | [14 empty] | Approved |  |  |  | No | Draft GP | [8 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
119 |  |  |  |  | Uitenhage (Erf 18613) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
120 |  |  |  |  | Uitenhage (Erf 1754) | [28 empty] | Town planning layouts are being prepared |  |  |  |  | New development. No community issues yet.
121 |  |  |  |  | Uitenhage (Erf 7927) | [33 empty] | New development. No community issues yet.
122 |  |  |  |  | Vaastrap | [33 empty] | Social instability. Current layout cannont accommodate all households.
123 |  |  |  |  | Moegesukkel (Uitenhage) | [33 empty] | Instability due to challenges of the servicability and availability of land.
124 |  |  |  |  | Moegesukkel (Bethelsdorp) | [33 empty] | Forms part of Bethelsdorp Ext 32, 34 & 36 project. Most people relocated.
125 |  |  |  |  | Edongweni | [33 empty] | Not developable as part of FST Report due to areas falling in pond areas.
126 |  |  |  |  | Enkuthazweni | [33 empty] | Not developable as part of FST Report due to areas falling in pond areas.
127 |  |  |  |  | Endulwini | [33 empty] | Not developable as part of FST Report due to areas falling in pond areas.
128 |  |  |  |  | Chris Hani (New Brighton Tipsite) | [33 empty] | Relocation project. Community resisted relocations.
129 |  |  |  |  | Ramaphosa (New Brighton) | [33 empty] | Relocation project. Community resisted relocations.
130 |  |  |  |  | Mayibuye | [33 empty] | Social instability.
131 |  |  |  |  | Silvertown Powerstation (Tip site) | [33 empty] | Relocation project. Community resisted relocations.
132 |  |  |  |  | Ngxazula (Uitenhage) | [33 empty] | Community instability due to demand for service delivery.
133 |  |  |  |  | Kleinskool Area K | [33 empty] | Small portion left out.
134 |  |  |  |  | Riemvaasmak | [33 empty] | Community residing on private land.
135 |  |  |  |  | Talliban | [33 empty] | Relocations project.
136 |  |  |  |  | Powerline NU8 | [33 empty] | Relocations project.
137 |  |  |  |  | Hlalani NU8 | [33 empty] | Relocations project.
138 |  |  |  |  | Walmwer Area N | [33 empty] | Forms part of Walmer Development.
139 |  |  |  |  | Westville | [33 empty] | Frequent community unrest demanding service delivery
140 |  |  |  |  | Creeky Valley
141 |  |  |  |  | James Mjo
142 |  |  |  |  | Moe Valley
143 |  |  |  |  | Joe Modise (Resevouir) | [33 empty] | No developable due to environmental issues
144 |  |  |  |  | Boo Plaas
Note on A1: temp:
Note on H4: temp: Provincial Department Of Human Settlements (PDOHS)
Note on H18: temp: Urban Settlement Development Grant (USGD)
Note on AJ49: nbonkolo: Stage 2 start date
Note on AJ57: nbonkolo: Stage 2 start date
Note on H65: temp: Urban Settlement Development Grant (USGD)