## USDG PLAN
NELSON MANDELA BAY MUNICIPALITY
URBAN SETTLEMENTS DEVELOPMENT GRANT PLAN 2018/19
Project Name | Overall Financial Target for 2018/19 as per | Overall Financial Target for 2018/19 as per | Overall Non financial Target for 2018/19 as per the | 1st Quarter | 1st Quarter | 2nd Quarter | 2nd Quarter | 3rd Quarter | 3rd Quarter | 4th Quarter | 4th Quarter
| SDBIP-USDG REVISED | SDBIP-USDG | SDBIP-USDG | Planned Financial -USDG | Planned Non financial - USDG | Planned Financial -USDG | Planned non Financial-USDG | Planned Financial -USDG | Planned non Financial-USDG | Planned Financial output | Planned Non Financial | 3% allocation | BUDGET EXCL 3% | BUDGET EXCL VAT
WATER AND SANITATION
Provision of bulk water and sanitation services for the upgrading of informal settlements | 566078449.9055 | 598911000 | 2500 | 56607844.9905 | 500 | 169823534.9716 | 1000 | 339647069.9433 | 1750 | 566078449.9055 | 2500 | 16982353.4972 | 549096096.4083 | 477474866.442
ROADS AND STORMWATER
Tarring of gravel roads | 86200378.0718 | 91200000 | 11.5 km | 8620037.8072 | 0 km | 25860113.4216 | 0 km | 51720226.8431 | 5 km | 86200378.0718 | 11.5 km | 2586011.3422 | 83614366.7297 | 72708144.9823
| 0 |  |  |  | (appoint-ment of contractors and site preparation) |  | (box cut and layer works) |  |  | 0
HUMAN SETTLEMENTS
Servicing of sites | 217500483.93 | 230520000 | 2500 | 21750048.393 | 500 | 65250145.179 | 1000 | 130500290.358 | 1750 | 217500483.93 | 2500 | 6525014.5179 | 210975469.4121 | 183456929.9236
(water, sanitation, basic roads) | 0 | [8 empty] | 0
HEALTH AND SOCIAL DEVELOPMENT
Development of Public Open Spaces | 20000000 | 20700000 | 10 Public Open Spaces | 2000000 | 0 | 6000000 | 2 Public Open Spaces | 12000000 | 4 Public Open Spaces | 20000000 | 10 Public Open Spaces | 600000 | 19400000 | 16869565.2174
| 0 |  |  |  | (Prioritisation of sites and procurement)
Development of Cemeteries | 5000000 | 5000000 | 1 Cemetery | 500000 | 0 | 1500000 | 20% completion | 3000000 | 50% completion | 5000000 | 1 Cemetery | 150000 | 4850000 | 4217391.3043
| 0 |  |  |  | (Prioritisation of sites and procurement)
ENERGY
Public lighting | 8884688.0907 | 9400000 | 960 installations | 2221172.0227 | 240 | 4442344.0454 | 480 | 6663516.0681 | 720 | 8884688.0907 | 960 | 266540.6427 | 8618147.448 | 7494041.2591
(Area and residential lighting) | 0 |  |  |  | installations |  | installations |  | installations |  | installations
Refurbishing of distribution sub-stations | 2000000 | 2000000 | 4 substations | 500000 | 1 substation | 1000000 | 2 substations | 1500000 | 3 substations | 2000000 | 4 substations | 60000 | 1940000 | 1686956.5217
0
Note: Dependent on the final USDG allocation to be published as per DoRA, 3% of the USDG Allocation will be used to cover operational expenses. | [11 empty] | 27169919.9999 |  | 763907895.6505
| 905663999.9981 | 957731000 | [9 empty] | 23626017.39

## MTSF
NELSON MANDELA BAY MUNICIPALITY - SUMMARY OF 5-YEAR MTSF TARGETS
MTSF TARGET 2019 | National 5 Yr MTSF Target for Metro | Annual MTSF Target | 2014/15 Achieved | 2015/16 Achieved | 2016/17 Achieved | 2017/18 Target | 2018/19 Target
750 000 households in informal settlements upgraded to Phase 2 of the Informal Settlements Upgrading Programme | 14 810 | 2 962
Individual households (serviced sites – not metered) |  |  | 4 035 | 3 003 | 4 004 | 2500 | 2500
Water and Sanitation
Total to date towards MTSF Target |  |  |  | Sub-total | 11 042
[5 empty] | 1 043 | (2017/18 Mid-year actual)
12 085
Individual Households
Water |  |  | 1 041 | 1 749 | 1 130 | 582 | 2 000
Sanitation |  |  | 1 041 | 1 749 | 1 130 | 582 | 2 000
Electricity |  |  | 2 215 | 1 945 | 3 432 | 2 000 | 2 000
Title Deeds:
563 000 for new developments |  |  | 894 | 528 | 856 | 1 000 | 1 000
Pre-1994 housing stock |  |  | 163 | 323 | 508 | 200 | 200
Post-1994 housing stock
10 000 of hectares of well-located land